RESTORATION OF HEALTH FACILITIES DESTROYED BY TSUNAMI 9.0

26th DECEMBER – 2004

Ministry of Healthcare Nutrition and Uva-Wellassa Development

Sri Lanka

The Government of Sri Lanka provides comprehensive health care to the population of Sri Lanka, through a network of preventive and curative health care facilities. There are 569 Medical Institutions with inpatient facilities, comprising 15 Teaching Hospitals, 06 Provincial Hospitals, 36 Base Hospitals, 157 District Hospitals, 102 Peripheral Units 173 Rural Hospitals, 90 Estate Hospitals and Specialized Hospitals.  In addition there are 406 Central Dispensaries which provide only out-patient care. There is a network of 276 Health Units (Medical Officer of Health Offices) which provides promotive and preventive health services through domiciliary and clinic care.

For Administrative purposes Sri Lanka is divided into 8 provinces and 26 Districts. The Tsunami Disaster on the 26th December 2004, affected 212,223 families, displacing 572,578 people and 30.615 deaths with 4356 persons missing. Health facilities in 14 out of 25 Districts were affected from the disaster following the tsunami tidal waves. Damage and destruction to infrastructure is extensive and many health facilities are damaged in all affected areas.

Among the affected health institutions were Hospitals, District Health (DPDHS) Offices, Health Units (Medical Officer of Health Offices), Regional Drug Stores, Staff Quarters and Maternal and Child Health Clinics. Several school dental clinics under the Department of Education were also damaged.

Some of these facilities need to be completely reconstructed, whereas some need only rehabilitation and renovation. Certain facilities need to be re-located.

The reconstruction and rehabilitation work involves, construction of buildings, provision of water supply, electricity, communication facilities, furniture, transport facilities, supplies and equipment.

This proposal provide, the extent of damage for the facilities, the needs for each institution and the proposed work to be undertaken and approximate costs, according to the Districts.

RESTORATION OF HEALTH FACILITIES OF SRI LANKA DESTROYED BY TSUNAMI 9.0- 26th DECEMBER – 2004

| Name of the District | Number of institutions Damaged |  |  | Restoration work to be done |  |  |  |  | Estimated Cost (Rs. Mn) | Reference Page number |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  | Fully Damaged | Partly Damaged |  | Re construction |  | Repair |  | Addition |  |  |
| Trincomalee | 03 | 06 |  | Buildings, Quarters, Drugs stores, Vehicles, Office equipment, Drugs, Medical and Surgical equipment |  | Electricity, Building, Sewerage Facilities |  |  | 1059.5 | 3 |
| Batticaloa | 09 | 10 |  | Buildings, Quarters, Drugs stores, Vehicles, Office equipment, Drugs, Medical and Surgical equipment |  | -do- |  |  | 1268.0 | 4 |
| Ampara | 11 | 02 |  | Buildings, Office equipment, Medical and Surgical equipment |  | -do- |  |  | 1683.0 | 6 |
| Kilinochchi | 01 |  |  | Buildings, Office equipment, Medical and Surgical equipment |  | -do- |  |  | 6.5 | 8 |
| Mulathivu | 06 | - |  | Buildings, Quarters, Drugs stores, Vehicles, Office equipment, Drugs, Medical and Surgical equipment |  | Electricity, Building, Sewerage Facilities |  |  | 462.0 | 9 |
| Jaffna |  | 04 |  | Buildings, Office equipment, Medical and Surgical equipment |  | -do- |  |  | 17.0 | 10 |
| Hambantota |  | 05 |  | Buildings, Office equipment, Medical and Surgical equipment |  | -do- |  |  | 22.5 | 11 |
| Matara | 02 | 05 |  | Buildings, Office equipment, Medical and Surgical equipment |  | -do- |  |  | 230.5 | 12 |
| Galle | 10 | 08 |  | Buildings, Office equipment, Medical and Surgical equipment |  | -do- |  |  | 1957.0 | 13 |
| Kalutara | 02 | 03 |  | Buildings, Office equipment, Medical and Surgical equipment |  | -do- |  |  | 28.5 | 15 |
| Colombo |  | 05 |  | Buildings, Office equipment, Medical and Surgical equipment |  | -do- |  |  | 22.5 | 16 |
| Drugs Lost due to Tsunami Tidal Waves |  |  |  |  |  |  |  |  | 173.0 |  |
| Total | 42 |  | 45 |  |  |  |  |  | 6757.0 |  |

Trincomalee District

Trincomalee District is situated in the northern most part of the Eastern Province. The total land area is 2529 sq.km with an inland water coverage of 96.7sq.km. It is a flat land with inlets of the sea forming the lagoons and bays which has helped in the formation of a world famous natural harbour.  The main city is Trincomalee and the urban population is 40%. The employment avenues are agriculture and fishing and the district produces a fair quantity of the country’s rice.

Trincomalee has 11 Divisional Secretary Divisions with 230 Grama Niladari areas comprising of 437 villages. The population is around 350,000 with 9 health units. The District comprises of the three main communities Sinhalese, Tamil and Muslim in equal proportion and was badly affected by the Tsunami tidal wave on 26th December 2004. Certain areas of the district such as Kinnya and Nilaveli areas were very severely affected with the health institutions in Kinnya being totally destroyed.

Altogether nine health institutions in the district were damaged and even though it was only partly damaged The General Hospital Trincomalee is the most important health facility in the district as it is the referral centre for the whole district.

Three health facilities, namely The District Hospital, and The MOH office in Kinnya and the MOH Office in Kuchcheveli were fully damaged, while six health facilities were partly damaged. These include other than The General Hospital,  the Rural Hospital in Kuchcheveli, the Central Dispensary in Thiriyaya, and the Gramodya Health Centres of Illangaihuramuhathuwara, Nagarkinnya and Fiza Nagarkinnya.

RESTORATION OF

HEALTH FACILITIES DESTROYED BY TSUNAMI 9.0- 26th DECEMBER - 2004 	TRINCOMALEE DISTRICT

| Name of the Facility | Present Status (Fully Damaged/Partly Damage) | Restoration work to be done |  |  | Estimated Cost (Rs. Mn) | Reference Page number |
| --- | --- | --- | --- | --- | --- | --- |
|  |  | # Re construction | Repair | Addition |  |  |
| District Hospital - Kinniya | Fully Damaged | Male and Female Wards, Paediatrict Ward, Gny & Obs. Wards, Mini OT, Labour room, admin Unit, General Store, Drugs stores, Staff quarters and other Units. | Repairing, re-wiring, Color washing |  | 215.0 | 18 |
| MOH Office Kinniya | Fully Damaged | MOH Office, MOH Quarters, Vehicle, Equip. Furniture’s, Electricity, etc.. | Repairing, re-wiring, Color washing |  | 33.0 | 19 |
| RH Kuchcheveli | Partly Damaged |  | Renovation of Building, replace windows & doors etc. |  | 33.0 | 19 |
| GH Trincomalee | Partly Damaged | Reconstruction of parapet wall Construction of a four storied building for wards | Repairing, re-wiring, Color washing |  | 760.0 | 19 |
| MOH - Kuchcheveli | Fully Damaged | MOH Office, MOH Quarters, Vehicle, Equip. Furniture’s, Electricity, etc.. |  |  | 2.5 | 20 |
| CD- Thiriyaya | Partly Damaged | Re-establish patient waiting room, consultation room, stores, Dispensary, etc. | Repairing, re-wiring, Color washing |  | 2.5 | 20 |
| GHC- Illangaihuramuhathuwaram | Partly Damaged | Clinic Centre with waiting room, examination room, store room, etc. | -do- |  | 4.5 | 20 |
| GHC- Nagarkinniya | Partly Damaged | -do- | -do- |  | 4.5 | 21 |
| GHC- Fiza Nagarkinnya | Partly Damaged | -do- | -do- |  | 4.5 | 21 |
| ## Total |  |  |  |  | 1059.5 |  |

RESTORATION OF HEALTH FACILITIES DESTROYED BY TSUNAMI 9.0- 26th DECEMBER - 2004 BATTICALOA DISTRICT

| Name of the Facility | Present Status (Fully Damaged /Partly Damage) | Restoration work to be done |  |  | Estimated Cost (Rs. Mn) | Reference Page Number |
| --- | --- | --- | --- | --- | --- | --- |
|  |  | # Re construction | Repair | Addition |  |  |
| District Hospital – Kattankudi | Partly Damaged | Building, Electricity & Power Supply, Water Supply, Purchasing Vehicles, Officer Equipment and Furniture etc. | Repair partly damaged buildings |  | 215.0 | 24 |
| District Hospital – Kallar | Fully Damaged | -- do -- |  |  | 215.0 | 24 |
| PU – Vakarai | Fully Damaged | Building, Ambulance, Equipment and Furniture, Vehicle, Electricity & Power Supply, Water Supply etc. |  |  | 145.0 | 25 |
| RH – Palameenmadu | Partly Damaged | Building, Electricity & Power Supply, Water Supply, etc. | Repair partly damaged buildings |  | 145.0 | 25 |
| Central Dispensary – Navalady | Fully Damaged | OPD with waiting room, examination room, AMO Quarters, Equipment, Furniture, Water & Electricity etc. |  |  | 9.0 | 26 |
| CD & MH – Thuraineelavanai | Partly Damaged | OPD with waiting room, examination room, AMO Quarters, Equipment, Furniture, Water & Electricity etc. | Repair partly damaged buildings |  | 9.0 | 26 |
| CD – Palamunai | Fully Damaged | OPD with waiting room, examination room, AMO Quarters, Equipment, Furniture, Water & Electricity etc. |  |  | 9.0 | 27 |
| MOH – Kalawanchikudy | Partly Damaged | Repairs to MOH and MOH Quarters, Vehicle, Equipment and Furniture, Electricity etc. | Repair partly damaged buildings |  | 33.0 | 27 |
| CD – Kathiravely | Partly Damaged | OPD with waiting room, examination room, AMO Quarters, Equipment, Furniture, Water & Electricity etc. |  |  | 9.0 | 28 |
| DH - Kaluwanchikudy | Partly Damaged | Building, Electricity & Power Supply, Water Supply, Purchasing Vehicles, Officer Equipment and Furniture etc. | Repair partly damaged buildings |  | 145.0 | 28 |
| DH – Arayampathy | Partly Damaged | Building, Electricity & Power Supply, Water Supply, Purchasing Vehicles, Officer Equipment and Furniture etc. | Repair partly damaged buildings |  | 145.0 | 29 |
| CD & MH – Kokkadichcholai | Partly Damaged | OPD with waiting room, examination room, AMO Quarters, Equipment, Furniture, Water & Electricity etc | Repair partly damaged buildings |  | 17.0 | 29 |
| DH – Valaichenai | Partly Damaged | Building, Electricity & Power Supply, Water Supply, Purchasing Vehicles, Officer Equipment and Furniture etc. | Repair partly damaged buildings |  | 145.0 | 30 |
| GHC – Maddikaly | Partly Damaged | Waiting room, examination room, store room, injection room, etc. |  |  | 4.5 | 30 |
| GHC – Thiruchenthui | Fully Damaged | -- do -- |  |  | 4.5 | 30 |
| GHC – Koddaikallar | Fully Damaged | -- do -- |  |  | 4.5 | 31 |
| GHC – Periyakallar | Fully Damaged | -- do -- |  |  | 4.5 | 31 |
| GHC – Kluthawalai | Fully Damaged | -- do -- |  |  | 4.5 | 31 |
| GHC – Valaichchenai | Fully Damaged | -- do -- |  |  | 4.5 | 32 |
| ## Total |  |  |  |  | 1268.0 |  |

RESTORATION OF HEALTH FACILITIES DESTROYED BY TSUNAMI 9.0- 26th DECEMBER - 2004 AMPARA DISTRICT

| Name of the Facility | Present Status (Fully Damaged/Partly Damage) | Restoration work to be done |  |  | Estimated Cost (Rs. Mn) | Reference Page Number |
| --- | --- | --- | --- | --- | --- | --- |
|  |  | # Re construction | Repair | Addition |  |  |
| Regional Medical Supply Division - Kalmunai | Fully Damaged | Building, Cold Room, Furniture and Office Equipment, Vehicles etc. |  |  | 75.0 | 35 |
| DH – Sainthamaranthu | Fully Damaged | Building, Electricity & Power Supply, Water Supply, Purchasing Vehicles, Office Equipment and Furniture etc. |  |  | 165.0 | 35 |
| DH – Ninthavur | Fully Damaged | -- do -- |  |  | 165.0 | 36 |
| PU – Maruthamunai | Fully Damaged | Building, Ambulances, Equipment, Furniture, Electricity Power, Office Equipment |  |  | 165.0 | 37 |
| PU – Karaitivu | Fully Damaged | -- do -- |  |  | 165.0 | 37 |
| CD & MH Periyaneelawanai | Fully Damaged | OPD with waiting room, examination room, AMO Quarters, Equipment, Furniture, Water & Electricity etc |  |  | 13.0 | 38 |
| CD & MH-Komari | Fully Damaged | -- do -- |  |  | 13.0 | 38 |
| DH – Pottuvil | Partly Damaged | Building, Electricity & Power Supply, Water Supply, Purchasing Vehicles, Office Equipment and Furniture etc | Repair partly damaged buildings |  | 145.0 | 38 |
| DH – Thirukkovil | Partly Damaged | -- do-- | Repair partly damaged buildings |  | 145.0 | 39 |
| MOH – Kalmunai South | Fully Damaged | Construction of MOH and MOH Quarters, Vehicle, Equipment and Furniture, Electricity etc. |  |  | 33.0 | 39 |
| MOH – Sainthamaruthvu | Fully Damaged | -- Do -- |  |  | 33.0 | 39 |
| MOH – Karaitivu | Fully Damaged | -- Do -- |  |  | 33.0 | 40 |
| MOH – Nintavur | Fully Damaged | -- Do -- |  |  | 33.0 | 40 |
| Other Public Health requirement (Sewerage System) |  |  |  | Water bed has elevated and difficult to maintain pit latrines or water seal latrines | 500.0 | 40 |
| ## Total |  |  |  |  | 1683.0 |  |

RESTORATION OF HEALTH FACILITIES DESTROYED BY TSUNAMI 9.0- 26th DECEMBER - 2004 KILINOCHCHI DISTRICT

| Name of the Facility | Present Status (Fully Damaged/Partly Damage) | Restoration work to be done |  |  | Estimated Cost (Rs. Mn) | Reference Page Number |
| --- | --- | --- | --- | --- | --- | --- |
|  |  | # Re construction | Repair | Addition |  |  |
| GHC – Chundikkulam | Fully Damaged | Clinic Center with waiting room, Examination Room, Stores Room, Equipment, Furniture etc. |  |  | 4.5 | 42 |
| Other Equipment | New |  |  | Generators, Motor Cycle, Furniture, Equipment | 2.0 | 42 |
| ## Total |  |  |  |  | 6.5 |  |

RESTORATION OF HEALTH FACILITIES DESTROYED BY TSUNAMI 9.0- 26th DECEMBER - 2004  MULLAITIVU DISTRICT

| Name of the Facility | Present Status (Fully Damaged/Partly Damage) | Restoration work to be done |  |  | Estimated Cost (Rs. Mn) | Reference Page Number |
| --- | --- | --- | --- | --- | --- | --- |
|  |  | # Re construction | Repair | Addition |  |  |
| DPDHS Office Mullaitivu | Fully Damaged | Construction of buildings, Furniture and Officer Equipment, Vehicles |  |  | 130.0 | 43 |
| Regional Medical supply Division Mullaitivu | Fully Damaged | Building, Cold Room, Furniture and Office Equipment, Vehicles etc. |  |  | 75.0 | 44 |
| DH – Mullaitivu | Fully Damaged | Buildings, Electricity & Power Supply, Purchasing Vehicles, Officer Equipment and Furniture etc. |  |  | 215.0 | 44 |
| MOH – Mullativu | Fully Damaged | Construction of MOH office and MOH Quarters, Vehicle, Equipment & Furniture, Electricity etc. |  |  | 33.0 | 45 |
| GHC – Irampalam | Fully Damaged | Clinic Center with waiting room, Examination Room, Store Room, Equipment, Furniture etc. |  |  | 4.5 | 45 |
| GHC - Alampan | Fully Damaged | -- do -- |  |  | 4.5 | 45 |
| ## Total |  |  |  |  | 462.0 |  |

RESTORATION OF HEALTH FACILITIES DESTROYED BY TSUNAMI 9.0- 26th DECEMBER - 2004 JAFFNA DISTRICT

| Name of the Facility | Present Status (Fully Damaged/Partly Damage) | Restoration work to be done |  |  | Estimated Cost (Rs. Mn) | Reference Page number |
| --- | --- | --- | --- | --- | --- | --- |
|  |  | # Re construction | Repair | Addition |  |  |
| District Hospital Velvatithurai | Partly damaged |  | Repairs to OPD building and clinic rooms |  | 4.0 | 47 |
| Peripheral Hospital Marathenkerny | Partly damaged |  | Repairs to OPD building and clinic rooms |  | 4.0 | 47 |
| GHC Sempianpattu | Partly Damaged |  | Clinic Centre with waiting room, examination room, store room, etc. |  | 4.5 | 48 |
| GHC- Uduthurai | Partly Damaged |  | -do- |  | 4.5 | 48 |
| ## Total |  |  |  |  | 17.0 |  |

RESTORATION OF HEALTH FACILITIES DESTROYED BY TSUNAMI 9.0- 26th DECEMBER - 2004 HAMBANTOTA DISTRICT

| Name of the Facility | Present Status (Fully Damaged/Partly Damage) | Restoration work to be done |  |  | Estimated Cost (Rs. Mn) | Reference Page number |
| --- | --- | --- | --- | --- | --- | --- |
|  |  | # Re construction | Repair | Addition |  |  |
| GHC Medaketiya | ### Partly Damage | Waiting room, examination room, store room, injection room, etc. |  |  | 4.5 | 50 |
| GHC Nakulugamuwa | ### Partly Damage | -do- |  |  | 4.5 | 50 |
| GHC Kudawella | ### Partly Damage | -do- |  |  | 4.5 | 50 |
| GHC Hambantota (West) | ### Partly Damage | -do- |  |  | 4.5 | 51 |
| GHC Kirinda | ### Partly Damage | -do- |  |  | 4.5 | 51 |
| ## Total |  |  |  |  | 22.5 |  |

RESTORATION OF HEALTH FACILITIES DESTROYED BY TSUNAMI 9.0- 26th DECEMBER - 2004 MATARA DISTRICT

| Name of the Facility | Present Status (Fully Damaged/Partly Damage) | Restoration work to be done |  |  | Estimated Cost (Rs. Mn) | Reference Page number |
| --- | --- | --- | --- | --- | --- | --- |
|  |  | # Re construction | Repair | Addition |  |  |
| DPDHS Office - Matara | Fully Damage | Building |  | Furniture and Office Equipment, Vehicles | 130.0 | 52 |
| Regional Drugs Store – Matara | Fully Damaged | Building and equipment |  | Furniture and Office Equipment, Vehicles | 75.0 | 53 |
| GHC Kamburugamuwa | Partly Damage | Waiting hall, examination hall, store room, injection room, etc. |  |  | 4.5 | 53 |
| GHC Galbokka | Partly Damage | -do- |  |  | 4.5 | 54 |
| GHC Batheegama | Partly Damage | -do- |  |  | 4.5 | 54 |
| MOH - Matara | Partly Damage | Waiting hall, examination hall, store room, injection room, etc. | Repair partly damaged buildings |  | 2.0 | 54 |
| GH Matara | Partly Damage | Furniture and Equipment | Repair and coluor washing |  | 10.0 | 55 |
| ## Total |  |  |  |  | 230.5 |  |

RESTORATION OF HEALTH FACILITIES DESTROYED BY TSUNAMI 9.0- 26th DECEMBER - 2004  GALLE DISTRICT

| Name of the Facility | Present Status (Fully Damaged/Partly Damage) | Restoration work to be done |  |  | Estimated Cost (Rs. Mn) | Reference Page number |
| --- | --- | --- | --- | --- | --- | --- |
|  |  | # Re construction | Repair | Addition |  |  |
| Teaching Hospital Mahamodara | Partly damaged |  |  | Re-locate the hospital with new Building, Office Equipment, Furniture and Vehicle | 1532.0 | 57 |
| MOH Office Hikkaduwa | Fully Damage | MOH Office, MOH Quarters, Vehicle, Equip. Furniture’s, Electricity, etc.. |  |  | 33.0 | 57 |
| MOH Balapitiya | Partly Damage | --do-- |  |  | 33.0 | 58 |
| Port Health Office Galle | Fully damaged | Construction of Building and Office Equipment, Furniture and Vehicle |  |  | 33.0 | 58 |
| Occupational Health Center Habaraduwa | Partly |  |  | Building, Office Furniture and Equipment, etc. | 33.0 | 58 |
| RH- Madampegama | Partly Damage | Building, Ambulances, Equipment, Furniture, Electricity Power, |  |  | 8.5 | 58 |
| CD Hikkaduwa | Partly Damage | OPD with waiting room, examination room, AMO Quarters, Equipment, Furniture, Water & Electricity etc. |  |  | 7.0 | 59 |
| CD- Ahangama | Partly Damage | OPD with waiting room, examination room, AMO Quarters, Equipment, Furniture, Water & Electricity etc. |  |  | 7.0 | 59 |
| CD- Ahungalla | Partly Damage | OPD with waiting room, examination room, AMO Quarters, Equipment, Furniture, Water & Electricity etc. |  |  | 7.0 | 59 |
| GHC Dodanduwa | Partly Damage | Clinic Centre with waiting room, examination room, store room, etc. |  |  | 4.5 | 60 |
| GHC Akurala | Partly Damage | Clinic Centre with waiting room, examination room, store room, etc. |  |  | 4.5 | 60 |
| GHC Godagama | Partly Damage | Clinic Centre with waiting room, examination room, store room, etc. |  |  | 4.5 | 60 |
| GHC Seenigama | Partly Damage | -do- |  |  | 4.5 | 61 |
| GHC Hikkaduwa | Partly Damage | -do- |  |  | 4.5 | 61 |
| GHC Madampagama | Partly Damage | -do- |  |  | 4.5 | 61 |
| GHC Kalupe | Partly Damage | -do- |  |  | 4.5 | 62 |
| GHC Pitiwela | Partly Damage | -do- |  |  | 4.5 | 62 |
| GHC- Kathaluwa | Partly Damage | -do- |  |  | 4.5 | 62 |
| GHC-Habaraduwa | Partly Damage | -do- |  |  | 4.5 | 63 |
| GHC- Ahangama | Partly Damage | -do- |  |  | 4.5 | 63 |
| Regional Training Centre | Need Relocation | Construction of Building and Office Equipment, Furniture and Vehicle |  |  | 84.0 | 64 |
| DPDHS Office- Galle | Need Relocation | Construction of Building and Office Equipment, Furniture and Vehicle |  |  | 130.0 | 65 |
| ## Total |  |  |  |  | 1957.0 |  |

RESTORATION OF HEALTH FACILITIES DESTROYED BY TSUNAMI 9.0- 26th DECEMBER - 2004  KALUTARA DISTRICT

| Name of the Facility | Present Status (Fully Damaged/Partly Damage) | Restoration work to be done |  |  | Estimated Cost (Rs. Mn) | Reference Page number |
| --- | --- | --- | --- | --- | --- | --- |
|  |  | # Re construction | Repair | Addition |  |  |
| Aluthgama Clinic Centre | Fully Damaged | Waiting room, examination room, store room, injection room, PHI’s Office, PHNS Office, PHM’s Residence, etc. |  |  | 7.0 | 67 |
| Maradana Clinic Centre | Fully Damaged | Waiting room, examination room, store room, injection room, PHI’s Office, PHNS Office, PHM’s Residence, etc. |  |  | 7.0 | 68 |
| GHC Uyankelle | Partly Damaged | Clinic Centre with waiting room, examination room, store room, etc. |  |  | 4.5 | 68 |
| GHC- Sagara Pedesa | Partly Damaged | --do-- |  |  | 4.5 | 68 |
| GHC- Magalkanda | Partly Damaged | --do-- |  |  | 4.5 | 69 |
| BH- Panadura | Party Damaged | Corridor and Mortuary Building |  |  | 1.0 | 69 |
| ## Total |  |  |  |  | 28.5 |  |

RESTORATION OF HEALTH FACILITIES DESTROYED BY TSUNAMI 9.0- 26th DECEMBER - 2004  COLOMBO DISTRICT

| Name of the Facility | Present Status (Fully Damaged/Partly Damage) | Restoration work to be done |  |  | Estimated Cost (Rs. Mn) | Reference Page number |
| --- | --- | --- | --- | --- | --- | --- |
|  |  | # Re construction | Repair | Addition |  |  |
| GHC Modara | Partly Damaged | Clinic Centre with waiting room, examination room, store room, etc. |  |  | 4.5 | 70 |
| GHC Egoda Uyana | Partly Damaged | -do- |  |  | 4.5 | 70 |
| GHC Katukurunda | Partly Damaged | -do- |  |  | 4.5 | 71 |
| GHC Angulana | Partly Damaged | -do- |  |  | 4.5 | 71 |
| GHC Uyana | Partly Damaged | -do- |  |  | 4.5 | 71 |
| ## Total |  |  |  |  | 22.5 |  |

# Trincomalee District Damages

District Hospital – Kinniya: 	  Completely Damaged.

Outpatients Department, In patients Services

Maternity Care (Anti natal, Labour Room and

Postnatal) Basic Laboratory Facilities,

Staff quarters

Current Status:

Temporally functioning the Out Patient Department in the library building

Facilities need to be re-established 	Male ward, female ward, Paediatrics ward,

Gynaecology & obstetrics ward,

Mini Operation Theatre, Labour room,

Administration unit,

General stores, Drug stores,

Pharmacy, Laboratory,

Out Patient Department,

Preliminary care unit,

Health education unit &

Dental unit

Staff quarters – DMO,

MO (2 quarters),

PHM,

Nursing Officers

Combine quarters for technical staff,

Minor employee

Estimated cost for reconstruction -	Buildings 				Rs.  150.0 m

(Please refer Annex 1&2)		Electricity & power supply 		Rs.    1.5 m

Water supply & Sewerage System	Rs.    10.0 m

Communication system		Rs.    1.5 m

Vehicle – ambulance			Rs.    4.0 m

Vehicle – double cab			Rs.    4.0 m

Furniture				Rs.    5.5 m

Medical Equipment			Rs.    30.0 m

Record Keeping System		Rs     1.5 m

Waste Management System		Rs     2.0 m

Landscaping				Rs.    5.0 m

Total                                 Rs. 215.0 m

=========

MOH –Office Kinniya	Completely damaged

Current Status :

Temporary functioning in a Gramodaya Health Centre building

Facilities need to be re-established	MOH office building & Quarters   	Rs. 30.0 m

(Please refer annex 4)			Vehicle (double cab)			Rs. 4.0 m

Equipment & furniture		Rs. 4.5 m

Electricity, water supply		Rs. 3.5 m

Consumables				Rs. 1.0 m

Total				Rs.33.0 m

=======

RH – Kuchcheveli	-  		Partly damaged,

Furniture & equipment washed off

Water supply has to be repaired

Current Status:

Out Patient Department is functioning at the same place.

Facilities need to be re-established 	Renovation of Building

Replace windows & doors

Colour washing,

Solar power unit			Rs. 30 .0m

Generator

Water supply

Re- furniture, mattresses & linen   	Rs. 2.0 m

Equipment				Rs. 1.0. m

Total 			Rs33.0 m

=======

GH – Trincomalee  -	  		Boundary wall, one two storied building is damaged

Some equipment & furniture washed off. The damaged building is very old and not suitable to use as a ward complex. Therefore it has to be demolished and construct a new ward complex

Current Status: Hospital is functioning except two wards.

Estimated cost for reconstruction	Reconstruction of parapet wall }

(Please refer annexure 6)		Four storied building  for wards	Rs.300.0 m

Equipment and furniture		Rs 250.0 m

Sewerage system			Rs 200.0 m

Additional support –vehicles 		Rs. 10.0 m

_________

Total	Rs.760.0 m

========

MOH - Kuchcheveli	 -   	Partly damaged, Kuchcaheveli Police is occupying at present.

Current Status:

Not functioning

Facilities need to be re-established	Minor repairs to MOH office building	Rs. 2.0 m.

Consumables					Rs. 0.5 m

Total			Rs.2.5 m

=======

CD – Thiriyaya  -	Partly damaged,

Furniture & equipment washed off

Current Status:

Functioning at the same place.

Facilities need to be re-established

OPD 	-	Repairs to the Patient waiting room,				Rs. 2.0 m

Dispensary, Clinic room, Observation unit,

Utility room & toilets

Equipment & consumables							Rs. 0.5 m

-----------

Total					Rs.2.5 m

=======

Gramodaya Health Centre

Illangaithuramuhathuwaram 		Partly damaged

Furniture & equipment washed off

Water and electricity services damaged

Current Status:

Not functioning.

Facilities need to be re-established	(Please refer Annex 3)

Building –  	Clinic centre with waiting room, examination room

Store room, Injection room & toilets 				Rs. 3.5 m

Public Health Midwife’s quarters

Equipment							Rs. 0.5 m

Furniture							Rs. 0.2 m

Water & electricity						Rs. 0.3 m

-----------

Total			Rs. 4.5 m

=======

Gramodaya Health Centre 	Nagarkinniya  - (Please refer Annex 3)

Partly damaged

Furniture & equipment washed off

Water and electricity services damaged

Current Status:

Not functioning.

Facilities need  to be re-established

Building –  	Clinic centre with waiting room, examination room

Store room, Injection room & toilets 				Rs. 3.5 m

Public Health Midwife’s quarters

Equipment							Rs. 0.5 m

Furniture							Rs. 0.2 m

Water & electricity						Rs. 0.3 m

-----------

Total 			Rs. 4.5 m

=======

Gramodaya Health Centre 	Fiza Nagarkinnya	(Please refer Annex 3)

Partly damaged

Furniture & equipment washed off

Water and electricity services damaged

Current Status:

Not functioning.

Facilities need  to be re-established:

Building –  	Clinic centre with waiting room, examination room

Store room, Injection room & toilets 				Rs. 3.5 m

Public Health Midwife’s quarters

Equipment							Rs. 0.5 m

Furniture							Rs. 0.2 m

Water & electricity						Rs. 0.3 m

-----------

Total 			Rs. 4.5 m

=======

Cost estimates for re construction of Government Medical Institutes in

Trincomalee District

| Institute | Total Cost Rs. (million) |
| --- | --- |
| District Hospital – Kinnya | 215.0 |
| MOH office – Kinnya | 33.0 |
| RH – Kuchcheveli | 33.0 |
| GH – Trincomalee | 760.0 |
| MOH – Kuchcheveli | 2.5 |
| CD- Tiriyaya | 2.5 |
| Gramodaya Health Centre Illangaithuramuhathuwaram | 4.5 |
| Gramodaya Health Centre- Nagarknniya | 4.5 |
| Gramodaya Health Centre Fiza Nagarknniya | 4.5 |
| Total | 1059.5 |

Batticaloa District

The Batticaloa district lies in the Eastern coast of the Island and is 2,610 Sq.Km. in area. It is situated 314 Km (195 Miles) from Colombo and occupies the central part of the Eastern Sri Lanka  covering a land area of approximately 2633.1 Km. The District accounts for 3.8% of the Country’s total land area. Batticaloa District has 12 Divisional Secretary Divisions with 339 Grama Niladari areas and 893 villages. Batticaloa town is a Municipal Council area. There are 9 MOH areas for the 12 DS divisions. It is also an agricultural and fishing area and is famous for its singing fish. The major part of the population is concentrated in the narrow strip between the sea and the lagoon and these areas were utterly devastated during the Tsunami tidal wave resulting in the loss of many lives and health institutions.

The fully damaged institutions in the district  includes District hospital Kallar, Peripheral Unit Vakarai, Central Dispensary Navalady, Central Dispensary Palamunai, Gramodya Health Centre(GHC) Thiruchenthui, GHC Koddaikallar, GHC Periyakallar, GHC Kluthawalai, and GHC Valachchenai.

The partly damaged institutions are, District Hospitals Kattankudy which has a capacity of 56 beds , DH Kaluwanchikudy  DH Ayampathy and DH Valaichenai, Rural Hospital Palameemadu MOH office Kalawanchikudy , Combined Central Dispensaries and Maternal Homes in Thuraineelavalady and Kokkadicholai,  Central Dispensary Kathiravely and Gramodya Health Centre in Maddikaly.

## Batticaloa District Damages

District Hospital -  Kattankudi  -   Damaged to Buildings, Ambulance,

Wards ( 56 beds)			Outdoor patient Department  and  quarters.

Indoor patient care, & wards ( male, female

Paediatric) equipment, furniture for (hospital to be

Relocated later),

Current Status:

Out Patient Department is functioning temporary in a building belong to the Education Office.

Facilities need to be re established    Male ward, female ward, paediatric ward,

Gynaecology & Obstetric ward. Mini

Operation theatre, labour room, administration unit,

General stores, drug stores, pharmacy, laboratory,

OPD, preliminary care unit, Health Education Unit,

& Dental Unit

Staff quarters – DMO, MO(2)

PHM, Nursing Officer

Combined quarters for technical staff

Minor Employees.

Estimated cost for reconstruction -	Buildings 				Rs.  150.0 m

(Please refer Annex 1&2)		Electricity & power supply 		Rs.    1.5 m

Water supply & Sewerage System	Rs.    10.0 m

Communication system		Rs.    1.5 m

Vehicle – ambulance			Rs.    4.0 m

Vehicle – double cab			Rs.    4.0 m

Furniture				Rs.    5.5 m

Medical Equipment			Rs.    30.0 m

Record Keeping System		Rs     1.5 m

Waste Management System		Rs     2.0 m

Landscaping				Rs.    5.0 m

Total                                 Rs. 215.0 m

=========

District Hospital Kallar   -   Damaged to buildings, Wards (36 beds),

Out door patients department, medical officers quarters

Indoor patient care, outdoor patient care, ambulance

Current Status:

Out Patient Department is functioning in a school building. The school building has to be released for education of the children and will be shifting to the part of a hospital building.

Facilities need to be re-established:	 OPD , Wards, Dispensary, Equipment, Furniture, &  Ambulance

Estimated cost for reconstruction -	Buildings 				Rs.  150.0 m

(Please refer annex 1&2)		Electricity & power supply 		Rs.    1.5 m

Water supply & Sewerage System	Rs.    10.0 m

Communication system		Rs.    1.5 m

Vehicle – ambulance			Rs.    4.0 m

Vehicle – double cab			Rs.    4.0 m

Furniture				Rs.    5.5 m

Medical Equipment			Rs.    30.0 m

Record Keeping System		Rs     1.5 m

Waste Management System		Rs     2.0 m

Landscaping				Rs.    5.0 m

Total                                 Rs. 215.0 m

=========

Peripheral Unit, Vakarai   		Complete destruction to buildings, ambulance, wards

(24 beds) Outdoor patient care and furniture and

Equipment washed off

Current status: Not functioning. Staff is conducting mobile health camps in refugee camps.

Facilities need to be re-established: - OPD & wards, dispensary, equipment & furniture &

Ambulance.

Estimated cost for reconstruction -	Buildings 				Rs.  80.0 m

(Please refer Annex 1&2)		Electricity & power supply 		Rs.    1.5 m

(Part of the hospital buildings		Water supply & Sewerage System	Rs.    10.0 m

Can be repaired)			Communication system		Rs.    1.5 m

Vehicle – ambulance			Rs.    4.0 m

Vehicle – double cab			Rs.    4.0 m

Furniture				Rs.    5.5 m

Medical Equipment			Rs.    30.0 m

Record Keeping System		Rs     1.5 m

Waste Management System		Rs     2.0 m

Landscaping				Rs.    5.0 m

Total                                 Rs. 145.0 m

=========

Rural Hospital – Palameenmadu  -	Indoor patient care (25 beds), outdoor patient care,

Ambulance, quarters of the assistant Medical Officer,

have been completely damaged.

Current Status:

Out Patient Department is functioning in the same location.

Facilities need to be re-established:  -	Renovation of buildings, Supply of Equipment

Furniture and Ambulance.

Estimated cost for reconstruction -	Buildings 				Rs.  80.0 m

(Please refer Annex 1&2)		Electricity & power supply 		Rs.    1.5 m

(Renovation will be done)		Water supply & Sewerage System	Rs.    10.0 m

Communication system		Rs.    1.5 m

Vehicle – ambulance			Rs.    4.0 m

Vehicle – double cab			Rs.    4.0 m

Furniture				Rs.    5.5 m

Medical Equipment			Rs.    30.0 m

Record Keeping System		Rs     1.5 m

Waste Management System		Rs     2.0 m

Landscaping				Rs.    5.0 m

Total                                 Rs. 145.0 m

=========

Central Dispensary – Navalady-	Buildings completely destroyed,

Furniture & equipment washed away

Current Status:

Completely destroyed. No place to start. Staff is conducting mobile clinics in refugee camps.

Facilities need to be re-established:  -OPD, Dispensary, Equipment & Furniture.

Estimated cost for reconstruction:

Building –  	OPD with waiting room, examination room

Store room, Injection room & toilets 				Rs. 8.0 m

Quarters for Assistant Medical Officer

Equipment							Rs. 0.5 m

Furniture							Rs. 0.2 m

Water & electricity						Rs. 0.3 m

-----------

Total			Rs. 9.0 m

=======

Central Dispensary and  Maternity Home – Thuraineelavanai – Furniture & equipment washed away, Indoor maternity care affected

Current Status: Partly destroyed. OPD started at the same location.

Facilities need to be re-established:  -Repairs to OPD, Dispensary, Maternity unit,

Supply of equipment & furniture.

Estimated cost for reconstruction:

Building –  	OPD with waiting room, examination room

Store room, Injection room & toilets 				Rs. 8.0 m

Quarters for Assistant Medical Officer

Equipment							Rs. 0.5 m

Furniture							Rs. 0.2 m

Water & electricity						Rs. 0.3 m

-----------

Total			Rs. 9.0 m

=======

Central Dispensary Palamunai  -	Completely damaged to buildings, Furniture and equipment washed away. Water supply and electricity affected.

Current Status:

Completely destroyed. OPD started in temporary building at another location (near sub post office).

Facilities need to be re-established:  Out Patient Services, restore electricity, water tank & pipe lines.

Estimated cost for reconstruction:

Building –  	OPD with waiting room, examination room

Store room, Injection room & toilets 				Rs. 8.0 m

Quarters for Assistant Medical Officer

Equipment							Rs. 0.5 m

Furniture							Rs. 0.2 m

Water & electricity						Rs. 0.3 m

-----------

Total			Rs. 9.0 m

=======

MOH office Kalawanchidudy-	Partly damaged buildings and fully damaged pickup,

preventive health care equipment and furniture washed

away.

Current Status:

Partly destroyed. Staff is conducting mobile clinics and the MOH is functioning in the same place.

Facilities need to be re-established: -	Preventive health care services, supply of a Pickup (4 wheel drive), furniture and equipment

Facilities need to be re-established	MOH office building & Quarters   	Rs. 30.0 m

(Please refer Annex 4)		Vehicle (double cab)			Rs. 4.0 m

Equipment & furniture		Rs. 4.5 m

Electricity, water supply		Rs. 3.5 m

Consumables				Rs. 1.0 m

Total				Rs.33.0 m

=======

CD – Kathiravely		- Partly damaged, equipment, drugs and furniture destroyed.

Current Status: Partly destroyed. OPD started at the same location.

Facilities need to be re-established:  -	Renovation of OPD building and quarters

Estimated cost for reconstruction:

Repairs to OPD building with waiting room, examination room

Repairs to quarters for Assistant Medical Officer				Rs. 8.0 m

Equipment							Rs. 0.5 m

Furniture							Rs. 0.2 m

Water & electricity						Rs. 0.3 m

-----------

Total			Rs. 9.0 m

=======

DH – Kalawanchikudy	-Partly Damaged. Equipment and furniture washed away.

Current Status: Partly destroyed. OPD started at the same location.

Facilities need to be re-established:  -	Renovation of Wards Outpatients Department, In patients Services, Maternity Care (Anti natal, Labour Room and 	Postnatal) Basic Laboratory Facilities, Staff quarters

Buildings to be renovated:  	Male ward, female ward, paediatrics ward,

Gynaecology   & obstetrics ward,

Mini operation theatre, Labour room,

Administration unit,

General stores, drug stores,

Pharmacy, Laboratory, OPD,

Estimated cost for reconstruction -	Buildings 				Rs.  80.0 m

(Please refer Annex 1&2)		Electricity & power supply 		Rs.    1.5 m

Water supply & Sewerage System	Rs.    10.0 m

Communication system		Rs.    1.5 m

Vehicle – ambulance			Rs.    4.0 m

Vehicle – double cab			Rs.    4.0 m

Furniture				Rs.    5.5 m

Medical Equipment			Rs.    30.0 m

Record Keeping System		Rs     1.5 m

Waste Management System		Rs     2.0 m

Landscaping				Rs.    5.0 m

Total                                 Rs. 145.0 m

=========

DH – Arayampathy 	-Buildings are partly damaged, furniture & equipment washed away.

Current Status: Partly destroyed. OPD started at the same location.

Facilities need to be re-established:  -	Renovation of Wards Outpatients Department, In patients Services, Maternity Care (Anti natal, Labour Room and 	Postnatal)

Buildings to be renovated:  	Male ward, female ward, paediatrics ward,

Gynaecology   & obstetrics ward,

Mini operation theatre, Labour room,

Administration unit, General stores, drug stores,

Pharmacy, Laboratory, OPD,

Estimated cost for reconstruction -	Buildings 				Rs.  80.0 m

(Please refer Annex 1&2)		Electricity & power supply 		Rs.    1.5 m

Water supply & Sewerage System	Rs.    10.0 m

Communication system		Rs.    1.5 m

Vehicle – ambulance			Rs.    4.0 m

Vehicle – double cab			Rs.    4.0 m

Furniture				Rs.    5.5 m

Medical Equipment			Rs.    30.0 m

Record Keeping System		Rs     1.5 m

Waste Management System		Rs     2.0 m

Landscaping				Rs.    5.0 m

Total                                 Rs. 145.0 m

=========

CD & MH Kokkadichcholai -	Buildings are partly damaged, furniture & equipment

washed away.

Current Status: Partly destroyed. OPD started at the same location.

Facilities need to be re-established:  -	Renovation of OPD building and quarters

Buildings to be renovated:  		Maternity Unit, OPD and Dispensary

Quarters of the Assistant Medical Officer

Quarters of the Public Health Midwife

Estimated cost for reconstruction:

Building –  	OPD with waiting room, examination room

Store room, Injection room & toilets 				Rs. 15.0 m

Quarters for Assistant Medical Officer

Quarters for Public Health Midwife

Equipment							Rs. 1.0 m

Furniture							Rs. 0.5 m

Water & electricity						Rs. 0.5 m

-----------

Total			Rs. 17.0 m

=======

DH Valaichenai	-Buildings are partly damaged. Furniture and equipment washed away.

Current Status:

Partly destroyed. OPD started at the same location. Need renovation to buildings and equipment to be supplied.

Estimated cost for reconstruction -	Buildings 				Rs.  80.0 m

(Please refer Annex 1&2)		Electricity & power supply 		Rs.    1.5 m

Water supply & Sewerage System	Rs.    10.0 m

Communication system		Rs.    1.5 m

Vehicle – ambulance			Rs.    4.0 m

Vehicle – double cab			Rs.    4.0 m

Furniture				Rs.    5.5 m

Medical Equipment			Rs.    30.0 m

Record Keeping System		Rs     1.5 m

Waste Management System		Rs     2.0 m

Landscaping				Rs.    5.0 m

Total                                 Rs. 145.0 m

=========

GHC  Maddikaly	-Preventive healthcare centre. Buildings are fully damaged.

Current Status: Completely destroyed. Not functioning.

Facilities need to be re-established:	New construction (a building )

Estimated cost for reconstruction: (Please refer Annex 3)

Building –  	Clinic centre with waiting room, examination room

Store room, Injection room & toilets 				Rs. 3.5 m

Public Health Midwife’s quarters

Equipment							Rs. 0.5 m

Furniture							Rs. 0.2 m

Water & electricity						Rs. 0.3 m

-----------

Total 			Rs. 4.5 m

=======

GHC Thiruchenthui -	Building is fully damaged,

Current Status: Completely destroyed. Not functioning.

Facilities need  to be re-established:  -	New construction (a building )

Estimated cost for reconstruction: (Please refer Annex 3)

Building –  	Clinic centre with waiting room, examination room

Store room, Injection room & toilets 				Rs. 3.5 m

Public Health Midwife’s quarters

Equipment							Rs. 0.5 m

Furniture							Rs. 0.2 m

Water & electricity						Rs. 0.3 m

-----------

Total 			Rs. 4.5 m

=======

GHC Koddaikallar -		Building is fully damaged

Current Status: Completely destroyed. Not functioning.

Facilities need to be reestablished  -	New construction (a building )

Estimated cost for reconstruction: (Please refer Annex 3)

Building –  	Clinic centre with waiting room, examination room

Store room, Injection room & toilets 				Rs. 3.5 m

Public Health Midwife’s quarters

Equipment							Rs. 0.5 m

Furniture							Rs. 0.2 m

Water & electricity						Rs. 0.3 m

-----------

Total 			Rs. 4.5 m

=======

GHC Periyakallar	-	Building is fully damaged

Current Status: Completely destroyed. Not functioning.

Facilities need  to be re-established:  -	New construction (a building )

Estimated cost for reconstruction: (Please refer Annex 3)

Building –  	Clinic centre with waiting room, examination room

Store room, Injection room & toilets 				Rs. 3.5 m

Public Health Midwife’s quarters

Equipment							Rs. 0.5 m

Furniture							Rs. 0.2 m

Water & electricity						Rs. 0.3 m

-----------

Total 			Rs. 4.5 m

=======

GHC Kaluthawalai	-	Building is fully damaged

Current Status: Completely destroyed. Not functioning.

Facilities need  to be re-established:  -	New construction (a building )

Estimated cost for reconstruction: (Please refer Annex 3)

Building –  	Clinic centre with waiting room, examination room

Store room, Injection room & toilets 				Rs. 3.5 m

Public Health Midwife’s quarters

Equipment							Rs. 0.5 m

Furniture							Rs. 0.2 m

Water & electricity						Rs. 0.3 m

-----------

Total 			Rs. 4.5 m

=======

GHC Valachchenai  -	Building is completely destroyed

Current Status: Completely destroyed. Not functioning.

Facilities need  to be re-established:  -	New construction (a building )

Estimated cost for reconstruction: (Please refer Annex 3)

Building –  	Clinic centre with waiting room, examination room

Store room, Injection room & toilets 				Rs. 3.5 m

Public Health Midwife’s quarters

Equipment							Rs. 0.5 m

Furniture							Rs. 0.2 m

Water & electricity						Rs. 0.3 m

-----------

Total 			Rs. 4.5 m

=======

Cost estimates for re construction of Government Medical Institutes in

Batticaloa District

| Institute | Total Cost Rs. (million) |
| --- | --- |
| District Hospital Kattankudy | 215.0 m |
| District Hospital Kallar | 215.0 m |
| Peripheral Unit Vakarai | 145.0 m |
| Rural Hospital Palameendadu | 145.0 m |
| Central Dispensary Navalady | 9.0 m |
| CD & MH Thuraineelavanai | 9.0 m |
| Central Dispensary Palamunai | 9.0 m |
| MOH Office Kalawanchidudy | 33.0 m |
| Central Dispensary Kathiravely | 9.0 m |
| District Hospital Kaluwanchikudy | 145.0 m |
| District Hospital Arayampathy | 145.0 m |
| CD & MH Kokkadiolai | 17.0 m |
| District Hospital Valaichnai | 145.0 m |
| Gramodya Health Centre(GHC) Maddilaky | 4.5 m |
| GHC Thiruchenthui | 4.5 m |
| GHC Koddaikallar | 4.5 m |
| GHC Periyakallar | 4.5 m |
| GHC Kalthawalai | 4.5 m |
| GHC Valachchenai | 4.5 m |
| Total | 1268.0 m |

AMPARA DISTRICT

Ampara district on the southeastern coast of Sri Lanka was directly in the path of the December 26 tsunami and was the first to be hit. Massive waves swept over the low-lying coast without warning, flattening buildings and sweeping people away. It was a fresh calamity in a district that has already been deeply scarred by 20 years of civil war.

Ampara district has Sinhala, Tamil and Muslim communities. The worst affected were mainly Tamils and Muslims living close to the coast—many of them fishermen and their families. Everywhere the scene was the same. Homes, hospitals, Hindu temples and other buildings shared the same fate.

Ampara District has two health divisions (DPDHS Areas), namely Ampara and Kalmunai.

At Kalmunai, the damage was severe. For up to a kilometre from the sea, all buildings had been destroyed. It was like the area had been carpet-bombed. The Karaitivu hospital near the coast was also badly damaged.

The Regional Medical Supplies building has been damaged. It needs renovation  and refurbishing.  Four District Hospitals, four Peripheral Units and two CD & MH were damaged. Four Medical Officers of Health Buildings have been damaged. Construction of MOH office building at a new location with all necessary facilities is needed. In addition several MCH Clinic Facilities were damaged.

Five Ambulances, a lorry and a van for drug distribution, and 2 Double Cabs for surveillance and outreach services are urgently required.

Ampara District Damages

Deputy Provincial Director Division - Kalmunai

Regional Medical Supplies Division’s Stores Building	-Completely damaged.

Current status: Completely destroyed. Supply of medicine & surgical items to the institutions in the DPDHS division has been affected. Temporally established at Ashrof Memorial Hospital, Kalmunai.

Facilities need to be re-established:  New building with cold room store facilities. Furniture equipment and vehicles have to be provided.

Facilities required

Building with Cold room facilities 				Rs. 50.0  Million

Refrigerators

Cold boxes

Office furniture

Computers – 2							Rs 5.0 Million

Telephone and Fax machine

Vehicle garage

Vehicles

2 Lorries

1 Van								Rs 20.0 Million

Fork lift

Total		Rs 75.0 Million

DH Sainthamarunthu	All the hospital building, drug stores and MO quarters have

been completely damaged.

Current Status:

OPD is temporally functioning at Sinnapullai mosque.

Facilities need to be re-established 	Male ward, female ward, Paediatrics ward,

Gynaecology & obstetrics ward,

Mini Operation Theatre, Labour room,

Administration unit, General stores, Drug stores,

Pharmacy, Laboratory, Out Patient Department,

Preliminary care unit, Health education unit &

Dental unit

Staff quarters –   DMO quarters and for two MOs

PHM,

Nursing Officers

Combine quarters for technical staff,

Minor employee

Estimated cost for reconstruction -	Buildings 				Rs.  100.0 m

(Please refer Annex 1&2)		Electricity & power supply 		Rs.    1.5 m

Water supply & Sewerage System	Rs.    10.0 m

Communication system		Rs.    1.5 m

Vehicle – ambulance			Rs.    4.0 m

Vehicle – double cab			Rs.    4.0 m

Furniture				Rs.    5.5 m

Medical Equipment			Rs.    30.0 m

Record Keeping System		Rs     1.5 m

Waste Management System		Rs     2.0 m

Landscaping				Rs.    5.0 m

Total                                 Rs. 165.0 m

=========

#### DH Ninthavur	-		Completely damaged Hospital Buildings, MO quarters,

Curative care.

Current Status:

OPD is temporally functioning at Al Humair school.

Need to Relocate the hospital with new buildings

Facilities need to be re-established 	Male ward, female ward, Paediatrics ward,

Gynaecology & obstetrics ward,

Mini Operation Theatre, Labour room,

Administration unit, General stores, Drug stores,

Pharmacy, Laboratory, Out Patient Department,

Preliminary care unit, Health education unit &

Dental unit

Staff quarters – DMO, and MO  quarters,

PHM,

Nursing Officers

Combine quarters for technical staff,

Minor employee

Estimated cost for reconstruction -	Buildings 				Rs.  100.0 m

(Please refer Annex 1&2)		Electricity & power supply 		Rs.    1.5 m

Water supply & Sewerage System	Rs.    10.0 m

Communication system		Rs.    1.5 m

Vehicle – ambulance			Rs.    4.0 m

Vehicle – double cab			Rs.    4.0 m

Furniture				Rs.    5.5 m

Medical Equipment			Rs.    30.0 m

Record Keeping System		Rs     1.5 m

Waste Management System		Rs     2.0 m

Landscaping				Rs.    5.0 m

Total                                 Rs. 165.0 m

=========

#### PU Maruthamunai	-		Completely damaged Hospital Buildings, MO quarters,

Curative care.

Current Status:

OPD is temporally functioning in a community hall at main street.

Facilities need to be re-established: -  Construction of hospital building at a new location with  all necessary facilities.

Estimated cost for reconstruction -	Buildings 				Rs.  100.0 m

(Please refer Annex 1&2)		Electricity & power supply 		Rs.    1.5 m

Water supply & Sewerage System	Rs.    10.0 m

Communication system		Rs.    1.5 m

Vehicle – ambulance			Rs.    4.0 m

Vehicle – double cab			Rs.    4.0 m

Furniture				Rs.    5.5 m

Medical Equipment			Rs.    30.0 m

Record Keeping System		Rs     1.5 m

Waste Management System		Rs     2.0 m

Landscaping				Rs.    5.0 m

Total                                 Rs. 165.0 m

#### =========

#### PU Karaitivu 		-		Completely damaged Hospital Buildings, MO quarters,

Curative care.

Current Status:

OPD is temporally functioning in a agrarian service building at main street.

Facilities need to be re-established: -  Construction of hospital building at a new location with  all necessary facilities.

Estimated cost for reconstruction -	Buildings 				Rs.  100.0 m

(Please refer Annex 1&2)		Electricity & power supply 		Rs.    1.5 m

Water supply & Sewerage System	Rs.    10.0 m

Communication system		Rs.    1.5 m

Vehicle – ambulance			Rs.    4.0 m

Vehicle – double cab			Rs.    4.0 m

Furniture				Rs.    5.5 m

Medical Equipment			Rs.    30.0 m

Record Keeping System		Rs     1.5 m

Waste Management System		Rs     2.0 m

Landscaping				Rs.    5.0 m

Total                                 Rs. 165.0 m

=========

#### CD & MH Periyaneelawanai-	Hospital Buildings are Completely damaged including,

#### MO quarters,

Current Status: Not functioning. Staff is conducting mobile clinics.

Facilities need to be re-established:   Construction of hospital building at a new location with  all necessary facilities.

Estimated cost for reconstruction:

Building –  	OPD with waiting room, examination room

Store room, Injection room & toilets 				Rs. 12.0 m

Quarters for Assistant Medical Officer

Equipment							Rs. 0.5 m

Furniture							Rs. 0.2 m

Water & electricity						Rs. 0.3 m

-----------

Total			Rs. 13.0 m

=======

#### CD & MH Komari		- Hospital Buildings and MO quarters are completely damaged

Current Status: 		Not functioning. Staff is conducting mobile clinics.

Facilities need to be re-established: Construction of hospital building at a new location with  all necessary facilities.

Estimated cost for reconstruction:

Building –  	OPD with waiting room, examination room

Store room, Injection room & toilets 				Rs. 12.0 m

Quarters for Assistant Medical Officer

Equipment							Rs. 0.5 m

Furniture							Rs. 0.2 m

Water & electricity						Rs. 0.3 m

-----------

Total			Rs. 13.0 m

=======

DH  Pottuvil		-Partly damaged – ward building, MO quarters, curative Care

Current Status: OPD is functioning at the same location.

Facilities need to be re-established:  - 	Reconstruction of ward  & quarters  building.

Estimated cost for reconstruction -	Buildings 				Rs.  80.0 m

(Please refer Annex 1&2)		Electricity & power supply 		Rs.    1.5 m

Water supply & Sewerage System	Rs.    10.0 m

Communication system		Rs.    1.5 m

Vehicle – ambulance			Rs.    4.0 m

Vehicle – double cab			Rs.    4.0 m

Furniture				Rs.    5.5 m

Medical Equipment			Rs.    30.0 m

Record Keeping System		Rs     1.5 m

Waste Management System		Rs     2.0 m

Landscaping				Rs.    5.0 m

Total                                 Rs. 145.0 m

=========

DH  Thirukkovil	-Wards, hospital buildings and MO quarters are partly damaged.

Current Status: OPD is functioning at the same location.

Facilities need to be re-established:  - 	Reconstruction of ward  & quarters building.

Estimated cost for reconstruction -	Buildings 				Rs.  80.0 m

(Please refer Annex 1&2)		Electricity & power supply 		Rs.    1.5 m

Water supply & Sewerage System	Rs.    10.0 m

Communication system		Rs.    1.5 m

Vehicle – ambulance			Rs.    4.0 m

Vehicle – double cab			Rs.    4.0 m

Furniture				Rs.    5.5 m

Medical Equipment			Rs.    30.0 m

Record Keeping System		Rs     1.5 m

Waste Management System		Rs     2.0 m

Landscaping				Rs.    5.0 m

Total                                 Rs. 145.0 m

=========

MOH  Kalmunai South	 - 	Office building and quarters are completely

Facilities need to be re-established:  - 	Construction of MOH office  building at a new location with   all necessary facilities

Facilities need to be re-established	MOH office building & Quarters   	Rs. 30.0 m

(Please refer Annex 4)			Vehicle (double cab)			Rs. 4.0 m

Equipment & furniture		Rs. 4.5 m

Electricity, water supply		Rs. 3.5 m

Consumables				Rs. 1.0 m

Total				Rs.33.0 m

=======

MOH  Sainthamaruthtu	 - 	Office building and quarters are completely damaged

Facilities need to be re-established: Construction of MOH office  building at a new location  with   all necessary facilities

Facilities need to be re-established	MOH office building & Quarters   	Rs. 30.0 m

(Please refer Annex 4)		Vehicle (double cab)			Rs. 4.0 m

Equipment & furniture		Rs. 4.5 m

Electricity, water supply		Rs. 3.5 m

Consumables				Rs. 1.0 m

Total				Rs.33.0 m

=======

MOH  Karaitivu	 - 	Office building and quarters are completely

Facilities need to be re-established: Construction of MOH office building at a new location with   all necessary facilities

Facilities need to be re-established	MOH office building & Quarters   	Rs. 30.0 m

(Please refer Annex 4)		Vehicle (double cab)			Rs. 4.0 m

Equipment & furniture		Rs. 4.5 m

Electricity, water supply		Rs. 3.5 m

Consumables				Rs. 1.0 m

Total				Rs.33.0 m

=======

MOH  Nintavur	 - 	Office building and quarters are completely

Facilities need to be re-established: Construction of MOH office building at a new location   with   all necessary facilities

Facilities need to be re-established	MOH office building & Quarters   	Rs. 30.0 m

(Please refer Annex 4)		Vehicle (double cab)			Rs. 4.0 m

Equipment & furniture		Rs. 4.5 m

Electricity, water supply		Rs. 3.5 m

Consumables				Rs. 1.0 m

Total				Rs.33.0 m

=======

Other Public Health Requirements:

Water bed of the city was already very high and after the Tsunami situation has become worst. All the septic tanks are over flowing and there is a high risk of diarrhoeal disease epidemic.

In order to improve personal hygiene a sewerage system for the city is highly recommended.

Total estimated cost of the sewerage system is 		Rs 500.0 m

Cost estimates for re construction of Government Medical Institutes in

Ampara District

| Institute | Total Cost Rs. (million) |
| --- | --- |
| Regional Medical Supplies Division (Drug Stores) | 75.0 m |
| DH Samanthamaruthu | 165.0 m |
| DH Ninthavur | 165.0 m |
| PU Maruthamunai | 165.0 m |
| PU Karaitivu | 165.0 m |
| CD & MH Periyaneelawanai | 13.0 m |
| CD & MH Komari | 13.0 m |
| DH Pottuvil | 145.0 m |
| DH Thirukkovil | 145.0 m |
| MOH Kalmunai South | 33.0 m |
| MOH Sainthamaruthtu | 33.0 m |
| MOH Karaitivu | 33.0 m |
| MOH Nintavur | 33.0 m |
| Other Public Health Requirements Sewerage System for Kalmunai city | 500.0 m |
| Total | 1683.0 m |

Kilinochchi District

Kilinochchi District is mainly un-cleared and under the control of the LTTE. It is bounded in the North by the Jaffna District, on the East by the Bay of Bengal and partly by Mullativu District, the West by Mannar and partly the Indian ocean and the south again by the Mullativu district.

Kilinochchi is mainly an agricultural area and had a farm school affiliated to the Jaffna university. The land area of Kilinochchi is 1205 Sq.Km

Only one institution in the area is damaged which is a Gramodya Health Centre.

##### Kilinochchi District Damages

Chundikulam- GHC 	Completely damaged

Facilities need  to be re-established: (Please refer Annex 3)

Building –  	Clinic centre with waiting room, examination room

Store room, Injection room & toilets 				Rs. 3.5 m

Public Health Midwife’s quarters

Equipment							Rs. 0.5 m

Furniture							Rs. 0.2 m

Water & electricity						Rs. 0.3 m

-----------

Total 			Rs. 4.5 m

=======

Other equipment required:

2 Nos. Generators 5 KV

Motor bike

Furniture				Rs 2.0 m

Equipment

Cost estimates for re construction of Government Medical Institutes in

Killinochchi District

| Institute | Total Cost Rs. (million) |
| --- | --- |
| Chundikulam- GHC | 4.5 m |
| Other equipment required | 2.0 m |
| Total | 6.5 m |

Mullativu District

Mullativu District similar to Kilinochchi is also mainly un-cleared and is controlled by the LTTE. It is situated in the Eastern Coastal area of the island and is bounded by the Bay of Bengal on the East and on the North and North West by the Kilinochchi District. The land area is 2415 Sq Km.

This district too depends mainly on agriculture and fishing for their livelihood and the Tsunami wave that came on 26th December has washed away most of the fishing villages and the boats belonging to the people.

All the Health Care Institutions in the district have been totally destroyed by Tsunami. These include The Deputy Provincial Director’s Office, The Regional Medical Supply Division and The District Hospital which is the main hospital of the region and also The MOH office in Mullativu and the Gramodya Health Centres in Irampalam and Alampan.

Mullaitivu District Damages

DPDHS Office - Mullaitivu	Building and vehicles completely damaged. DPDHS office, drug stores and the DH Mullaitivu have temporally shifted to Pudukudiruppu hospital.

Building							Rs. 50 million

Furniture & Equipment:-

Air conditioned conference room

Conference table with PA system

Computer system with 10 ten terminals

2 Photocopiers (1heavy duty)

1 Risograph, 1 Fax machine, 2 typewriters

Office furniture

Stationary

Filing cabinet

Steel cabinet

Iron safe

Standby generator						Rs 30 million

Refrigerators- 2

Television – 1, DVD player – 1

Video player – 1, Multimedia Projectors– 1

Magee boards – 5

Overhead projectors -2

Digital camera – 1

Water filters - 3

Electric Kettles – 3

Crockery

Cutlery

Intercom system(25 nodes)

Vehicles

Lorries – 2, DPD vehicle – 1

Regional Epidemiologist – 1

MO/MCH – 1

Regional Dental Surgeon -1					Rs 50.0 million

Health Education Officer – 1

Vans – 2, Van with audio visual equipment -1

Anti Rabies Campaign – 2

Total		Rs 130.0 million

Regional Drug Stores

Facilities required

Building with Cold room facilities 				Rs. 50.0  Million

Refrigerators, Cold boxes

Office furniture, Computers – 2				Rs 5.0 Million

Telephone, Fax machine

Vehicle garage

Vehicles

2 Lorries

1 Van								Rs 20.0 Million

Fork lift

Total		Rs 75.0 Million

District Hospital Mullaitivu – Completely destroyed. Hospital has to rebuild at new location.

Current Status:  Work of the hospital has been taken over by Pudukudiruppu District Hospital.

Estimated cost for reconstruction -	Buildings 				Rs.  150.0 m

(Please refer Annex 1&2)		Electricity & power supply 		Rs.    1.5 m

Water supply & Sewerage System	Rs.    10.0 m

Communication system		Rs.    1.5 m

Vehicle – ambulance			Rs.    4.0 m

Vehicle – double cab			Rs.    4.0 m

Furniture				Rs.    5.5 m

Medical Equipment			Rs.    30.0 m

Record Keeping System		Rs     1.5 m

Waste Management System		Rs     2.0 m

Landscaping				Rs.    5.0 m

Total                                 Rs. 215.0 m

=========

MOH Office Mullaitivu	Completely damaged

Facilities need to be re-established: Construction of MOH office building at a new location   with all necessary facilities

Facilities need to be re-established	MOH office building & Quarters   	Rs. 30.0 m

(Please refer Annex 4)		Vehicle (double cab)			Rs. 4.0 m

Equipment & furniture		Rs. 4.5 m

Electricity, water supply		Rs. 3.5 m

Consumables				Rs. 1.0 m

Total				Rs.33.0 m

=======

Gramodya Health Centre Irampalan 	Completely damaged

Facilities need  to be re-established: 	New building

Estimated cost for reconstruction: (Please refer Annex 3)

Building –  	Clinic centre with waiting room, examination room

Store room, Injection room & toilets 				Rs. 3.5 m

Public Health Midwife’s quarters

Equipment							Rs. 0.5 m

Furniture							Rs. 0.2 m

Water & electricity						Rs. 0.3 m

-----------

Total 			Rs. 4.5 m

=======

Gramodya Health Centre Alampan	Completely destroyed

Facilities need  to be re-established:	New building

Estimated cost for reconstruction: (Please refer Annex 3)

Building –  	Clinic centre with waiting room, examination room

Store room, Injection room & toilets 				Rs. 3.5 m

Public Health Midwife’s quarters

Equipment							Rs. 0.5 m

Furniture							Rs. 0.2 m

Water & electricity						Rs. 0.3 m

-----------

Total 			Rs. 4.5 m

=======

Cost estimates for re construction of Government Medical Institutes in

Mullaitivu District

| Institute | Total Cost Rs. (million) |
| --- | --- |
| DPDHS Office Mullaitivu | 130.0 m |
| Regional Medical Supplies Division (Stores) | 75.0 m |
| District Hospital Mullaitivu | 215.0 m |
| MOH Mullaitivu | 33.0 m |
| GHC Iramplan | 4.5 m |
| GHC Alampalan | 4.5 m |
| Total | 462.0 m |

JAFFNA DISTRICT

Jaffna District, the northernmost region of the Island of Sri Lanka, is one of the oldest habitation sites in Lower South Asia, populated by Tamil speaking people. Jaffna is situated within ten degrees of latitude to the north of the equator. It is in close proximity to the sub-continent of India and separated from it by the Palk Strait and the Bay of Bengal.

The peninsula is actually almost an island with only a narrow causeway known as Elephant Pass . Jaffna is low lying; much of it covered by shallow lagoons, and has a number of interesting islands dotted offshore. In all it covers 2560 square km (999 square miles). With just under 900,000 inhabitants, the district of Jaffna is one of the most densely populated areas of Sri Lanka, second only to Greater Colombo.

The coastal region of the Jaffna peninsula was badly damaged by the Tsunami tidal wave on 26th December and four health institutions were damaged. These include The district hospital in Velvetithurai, Peripheral Unit in Marathenkerny, and the two Gramodya Health Centres in Sempianpatti and Uduthurei.

Jaffna District Damages

District Hospital - Velvetithurai 	Functioning, Partly damaged

Furniture & equipment washed away

Facilities need  to be re-established:

Repairs to OPD Building, Clinic rooms,

Store room, Injection room & toilets 				Rs. 3.0 m

Equipment							Rs. 0.5 m

Furniture							Rs. 0.5 m

-----------

Total 			Rs. 4.0 m

=======

Peripheral Unit - Marathankerni 	Functioning

Partly damaged

Furniture & equipment washed away

Facilities need  to be re-established:

Repairs to OPD Building, Clinic rooms,

Store room, Injection room & toilets 				Rs. 3.0 m

Equipment							Rs. 0.5 m

Furniture							Rs. 0.5 m

-----------

Total 			Rs. 4.0 m

=======

Gramodaya Health Centre - Sempianpattu 	Not functioning

Partly damaged

Furniture & equipment washed away

Facilities need  to be re-established:	(Please refer Annex 3)

Building –  	Clinic centre with waiting room, examination room

Store room, Injection room & toilets 				Rs. 3.5 m

Public Health Midwife’s quarters

Equipment							Rs. 0.5 m

Furniture							Rs. 0.2 m

Water & electricity						Rs. 0.3 m

-----------

Total 			Rs. 4.5 m

=======

Gramodaya Health Centr - Uduthurai 	Not functioning

Partly damaged

Furniture & equipment washed away

Facilities need  to be re-established:	(Please refer Annex 3)

Building –  	Clinic centre with waiting room, examination room

Store room, Injection room & toilets 				Rs. 3.5 m

Public Health Midwife’s quarters

Equipment							Rs. 0.5 m

Furniture							Rs. 0.2 m

Water & electricity						Rs. 0.3 m

-----------

Total 			Rs. 4.5 m

=======

Cost estimates for re construction of Government Medical Institutes in

Jaffna District

| Institute | Cost Rs (million) |
| --- | --- |
| District Hospital Velvatithurai | 4.0 m |
| Peripheral Unit Marathenkerny | 4.0 m |
| Gramodaya Health Centre Sempianpattu | 4.5 m |
| Gramodaya Health Centre Uduthurei | 4.5 m |
| Total | 17.0 m |

HAMBANTOTA DISTRICT

Hambantota district is located about 240 kilometres south of Sri Lanka’s capital Colombo. One of the country’s most remote and poorest regions, the majority of its population lead a hand-to-mouth existence surviving through fishing, small-scale agriculture, salt farming or tourism. Located next to Yala National Park, Sri Lanka’s second largest wild life reserve, the area attracts thousands of visitors each year.

But while tourists come to enjoy its pristine beauty, water shortages constantly plague the district. Over one-third of the 533,000-strong population live below the poverty line, 26.3 percent of all households are officially categorized as poor, and youth unemployment is rampant. The district records one of the country’s highest suicides rates, mainly due to endemic poverty.

The devastating impact of the tsunami has now pushed the area’s population even deeper into the abyss. Today Hambantota is like a war zone with hundreds of pulverised homes and dwellings, upturned vehicles, uprooted telegraph and phone lines and countless corpses floating in nearby lagoons and mangrove swamps.

Mainly the preventive health services were affected in Hambantota. One MOH building and 5 Gramodaya Health Centres were damaged.

To recover these services which provide maternal and child health care, needs about Rs. 4.5m. each. The Building comprises of the Clinic centre with waiting room, examination room, store room, injection room & toilets. The Public Health Midwife’s quarters also needs to be constructed along with the clinic building. Equipments, furniture, water & electricity supplies need to be provided.

Hambantota District Damages

MOH Tangalla

Gramodaya Health Centre – Medaketiya		Not functioning

Partly damaged, Furniture & equipment washed away

Water and electricity services have to be provided

Facilities need  to be re-established:	(Please refer Annex 3)

Building –  	Clinic centre with waiting room, examination room

Store room, Injection room & toilets 				Rs. 3.5 m

Public Health Midwife’s quarters

Equipment							Rs. 0.5 m

Furniture							Rs. 0.2 m

Water & electricity						Rs. 0.3 m

-----------

Total 			Rs. 4.5 m

=======

Gramodaya Health Centre – Nakulugamuwa	Not functioning

Partly damaged

Furniture & equipment washed away

Water and electricity services have to be provided

Facilities need  to be re-established:	(Please refer Annex 3)

Building –  	Clinic centre with waiting room, examination room

Store room, Injection room & toilets 				Rs. 3.5 m

Public Health Midwife’s quarters

Equipment							Rs. 0.5 m

Furniture							Rs. 0.2 m

Water & electricity						Rs. 0.3 m

-----------

Total 			Rs. 4.5 m

=======

Gramodaya Health Centre – Kudawella	Not functioning

Partly damaged , Furniture & equipment washed away

Water and electricity services have to be provided

Facilities need  to be re-established:	(Please refer Annex 3)

Building –  	Clinic centre with waiting room, examination room

Store room, Injection room & toilets 				Rs. 3.5 m

Public Health Midwife’s quarters

Equipment							Rs. 0.5 m

Furniture							Rs. 0.2 m

Water & electricity						Rs. 0.3 m

-----------

Total 			Rs. 4.5 m

=======

MOH – Hambantota

Gramodaya Health Centre – Hambantota  (West)	Not functioning

Partly damaged

Furniture & equipment washed away

Water and electricity services have to be provided

Facilities need  to be re-established:	(Please refer Annex 3)

Building –  	Clinic centre with waiting room, examination room

Store room, Injection room & toilets 				Rs. 3.5 m

Public Health Midwife’s quarters

Equipment							Rs. 0.5 m

Furniture							Rs. 0.2 m

Water & electricity						Rs. 0.3 m

-----------

Total 			Rs. 4.5 m

=======

MOH – Tissamaharama

Gramodaya Health Centre – Kirinda	Not functioning

Partly damaged

Furniture & equipment washed away

Water and electricity services have to be provided

Facilities need  to be re-established: (Please refer Annex 3)

Building –  	Clinic centre with waiting room, examination room

Store room, Injection room & toilets 				Rs. 3.5 m

Public Health Midwife’s quarters

Equipment							Rs. 0.5 m

Furniture							Rs. 0.2 m

Water & electricity						Rs. 0.3 m

-----------

Total 			Rs. 4.5 m

=======

Cost estimates for re construction of Government Medical Institutes in

Hamabantota District

| Institute | Cost Rs (million) |
| --- | --- |
| Gramodaya Health Centre - Medaketiya | 4.5 |
| Gramodaya Health Centre - Nakulugamuwa | 4.5 |
| Gramodaya Health Centre - Kudawella | 4.5 |
| Gramodaya Health Centre – Hambantota (West) | 4.5 |
| Gramodaya Health Centre - Kirinda | 4.5 |
| Total | 22.5 |

MATARA DISTRICT

Seven health facilities in the district were affected. The District Health Office (DPDHS) and the Regional Drug Stores which are located inside the Matara Fort close to the sea were completely damaged. These need to be re-constructed in a new location.

The Office of the Medical Officer of Health Matara and 3 Gramodaya Health Centres which provide maternal and child health services were partly damaged.

Matara District Damages

DPDHS Office	Building and vehicles completely damaged. The DPDHS Office is temporally functioning at Chest Clinic Matara damaged.

Building							Rs. 50 million

Furniture & Equipment:-

Air conditioned conference room

Conference table with PA system

Computer system with 10 ten terminals

2 Photocopiers (1heavy duty)

1 Risograph, 1 Fax machine

Office furniture, 2 typewriters

Stationary, Filing cabinet, Steel cabinet

Iron safe

Standby generator						Rs 30 million

Refrigerators- 2

Television – 1, DVD player – 1

Video player – 1, Multimedia Projectors– 1

Magee boards – 5

Overhead projectors -2

Digital camera – 1

Water filters – 3, Electric Kettles – 3

Crockery, Cutlery

Intercom system(25 nodes)

Vehicles

Lorries – 2, DPD vehicle – 1

Regional Epidemiologist – 1

MO/MCH – 1

Regional Dental Surgeon -1					Rs 50.0 million

Health Education Officer – 1

Vans – 2, Van with audio visual equipment -1

Anti Rabies Campaign – 2

Total		Rs 130.0 million

Regional Drug Stores

Facilities required:

Building with Cold room facilities 				Rs. 50.0  Million

Equipment:

Refrigerators

Cold boxes

Office furniture

Computers – 2							Rs 5.0 Million

Telephone

Fax machine

Vehicle garage

Vehicles

2 Lorries

1 Van								Rs 20.0 Million

Fork lift

Total		Rs 75.0 Million

Kamburugamuwa GHC		Not functioning

Partly damaged

Washed off- furniture &    equipment

Water and electricity services have to be provided

Facilities need  to be re-established:	(Please refer Annex 3)

Building –  	Clinic centre with waiting room, examination room

Store room, Injection room & toilets 				Rs. 3.5 m

Public Health Midwife’s quarters

Equipment							Rs. 0.5 m

Furniture							Rs. 0.2 m

Water & electricity						Rs. 0.3 m

-----------

Total 			Rs. 4.5 m

=======

Galbokka GHC	Not functioning

Partly damaged

Washed off- furniture &    equipment

Water and electricity services have to be provided

Facilities need  to be re-established:	(Please refer Annex 3)

Building –  	Clinic centre with waiting room, examination room

Store room, Injection room & toilets 				Rs. 3.5 m

Public Health Midwife’s quarters

Equipment							Rs. 0.5 m

Furniture							Rs. 0.2 m

Water & electricity						Rs. 0.3 m

-----------

Total 			Rs. 4.5 m

=======

Dickwella Batheegama GHC	Not functioning

Partly damaged

Washed off- furniture &    equipment

Water and electricity services have to be provided

Facilities need  to be re-established:	(Please refer Annex 3)

Building –  	Clinic centre with waiting room, examination room

Store room, Injection room & toilets 				Rs. 3.5 m

Public Health Midwife’s quarters

Equipment							Rs. 0.5 m

Furniture							Rs. 0.2 m

Water & electricity						Rs. 0.3 m

-----------

Total 			Rs. 4.5 m

=======

MOH Office Matara		Functioning

Partly damaged

Washed off- furniture &    equipment

Water and electricity services have to be provided

Facilities need  to be re-established:	(Please refer Annex 3)

Building –  	Clinic centre with waiting room, examination room

Store room, Injection room & toilets 				Rs. 3.5 m

Public Health Midwife’s quarters

Equipment							Rs. 0.5 m

Furniture							Rs. 0.2 m

Water & electricity						Rs. 0.3 m

-----------

Total 			Rs. 4.5 m

=======

GH Matara			Functioning

Partly damaged

Furniture & equipment of two wards merged under water

Facilities need  to be re-established:

Building repairs, 				Rs. 7.0 m

supply of furniture and equipment to two wards		Rs  3.0 m

-----------

Total 			Rs. 10.0 m

=======

Cost estimates for re construction of Government Medical Institutes in

Matara District

| Institute | Cost Rs (million) |
| --- | --- |
| DPDHS Office Matara | 130.0 m |
| Regional Drug Stores:- Building & equipment | 75.0 m |
| Gramodaya Health Centre- Damboragamuwa | 4.5 m |
| Gramodaya Health Centre- Galbokka | 4.5 m |
| Gramodaya Health Centre- Dickwella Batheegama | 4.5 m |
| MOH Office Matara | 2.0 m |
| General Hospital Matar | 10.0 m |
| Total | 230.5 m |

GALLE DISTRICT

Ten health institutions have been fully damaged, and 12 partly damaged.  The Teaching Hospital Mahamodara, located very close to the sea, which houses the Maternity and Gyanaecological Units, suffered extensive damage to the ground floor facilities, including furniture, equipment and supplies. It is proposed to relocate this hospital. A separate proposal will be developed.

The Port Health Office Galle and the 2 Offices of the Medical Offices of Health in Hikkaduwa and Balapitiya were completely damaged. These need to be reconstructed, preferably in a new location. Further the Occupational Health Center which provides Outpatient Services, and houses the office of the Rabies Control Programme may need relocation and reconstruction.

Eleven Clinic facilities have been damaged. Many of these clinics which provide maternal and child health care are small facilities in old buildings provided by the local authorities. When these are reconstructed it is proposed to set up Gramodaya Health Centres, which provide the above clinic facilities and in addition residential facilities for the Public Health Midwife.

The present District Health Office (DPDHS), which was flooded and partly damaged is an old building. This may be relocated. The Regional Training Centre is housed in the upper floor of the present DPDHS building, and is not suitable for training centre of this magnitude. This caters as a Regional Training centre for the whole province. It is proposed that a tailor-made RTC is put up instead of renovating the present old building.

Galle District Damages

Teaching Hospital – Mahamodara: 	Partly Damaged.

Outpatients Department, In-patients Services

Maternity Care (Anti natal, Labour Room and

Postnatal) Basic Laboratory Facilities,

Staff quarters

Current Status:

Temporally functioning the maternity unit at Teaching Hospital Karapitiya.

Facilities need to be re-established 	Antenatal wards, Post natal wards,

Gynaecology wards, Special Care Units

Operation Theatres, Labour rooms,

Intensive Care Units, Premature Baby Care Units

Administration unit,

General stores, Drug stores,

Pharmacy, Laboratory,

Out Patient Department,

Health education unit

Staff quarters

Estimated cost for reconstruction -	Buildings 				Rs. 868.0 m

(Please refer Annex 5)		Electricity & power supply 		Rs.    5.0 m

Water supply & Sewerage System	Rs. 150.0 m

Communication system		Rs.    3.5 m

Vehicle – ambulance			Rs.    20.0 m

Vehicle – double cab and Lorry	Rs.    10.0 m

Furniture				Rs.    10.0 m

Medical Equipment			Rs.    430.0 m

Record Keeping System		Rs     5.5 m

Waste Management System		Rs     10.0 m

Landscaping				Rs.    20.0 m

Total                                 Rs. 1532.0 m

=========

MOH Office -  Hikkaduwa 		Completely damaged and need to be re-located.

Furniture & equipment washed away

Water and electricity services have to be provided

Facilities need to be re-established	MOH office building & Quarters   	Rs. 30.0 m

(Please refer Annex 4)		Vehicle (double cab)			Rs. 4.0 m

Equipment & furniture		Rs. 4.5 m

Electricity, water supply		Rs. 3.5 m

Consumables				Rs. 1.0 m

Total				Rs.33.0 m

=======

MOH Office -  Balapitiya 		Partly damaged and need to be re-located.

Furniture & equipment washed away

Water and electricity services have to be provided

Facilities need to be re-established:	MOH office building & Quarters   	Rs. 30.0 m

(Please refer Annex 4)		Vehicle (double cab)			Rs. 4.0 m

Equipment & furniture		Rs. 4.5 m

Electricity, water supply		Rs. 3.5 m

Consumables				Rs. 1.0 m

Total				Rs.33.0 m

=======

Port Health Office – Galle Port 	Completely damaged and need to be re-located.

Furniture & equipment washed away

Water and electricity services have to be provided

Facilities need to be re-established	Office building & Quarters   		Rs. 30.0 m

(Please refer Annex 3)		Vehicle (double cab)			Rs. 4.0 m

Equipment & furniture		Rs. 4.5 m

Electricity, water supply		Rs. 3.5 m

Consumables				Rs. 1.0 m

Total				Rs.33.0 m

=======

Occupational Health Centre and Rabies control office -  Habraduwa

Completely damaged and need to be re-located. Furniture & equipment washed away,

Water and electricity services have to be provided

Facilities need to be re-established	Office building & Quarters   		Rs. 30.0 m

(Please refer Annex 3)		Vehicle (double cab)			Rs. 4.0 m

Equipment & furniture		Rs. 4.5 m

Electricity, water supply		Rs. 3.5 m

Consumables				Rs. 1.0 m

Total				Rs.33.0 m

=======

Rural Hospital – Madampegama  -	 OPD is functioning at the same place

Partly damaged,

Furniture & equipment washed away

Water and electricity services have to be provided

Facilities need to be re-established

OPD	-	Patient waiting room, Consultation room, Stores 		Rs. 5.0 m

Dispensary, Clinic room, Observation unit,

Utility room & toilets

Restoring of electricity, water supply and communication			Rs. 0.5 m

Medical Officers quarters 							Rs. 2.5 m

Equipment 									Rs. 0.5 m

-----------

Total					Rs.8.5 m

=======

Central Dispensary – Hikkaduwa 	Not functioning

Partly damaged,

Furniture &    equipment washed away

Water and electricity services have to be provided

Facilities need  to be re-established

OPD	-	Patient waiting room, Consultation room, Stores 		Rs. 3.5 m

Dispensary, Clinic room, Observation unit,

Utility room & toilets

Restoring of electricity, water supply and communication			Rs. 0.5 m

Medical Officers quarters 							Rs. 2.5 m

Equipment 									Rs. 0.5 m

-----------

Total					Rs.7.0 m

=======

Central Dispensary – Ahangama -	 Functioning at a temporary building.

Completely damaged,

Furniture &    equipment washed away

Water and electricity services have to be provided

Facilities need  to be re-established:

OPD	-	Patient waiting room, Consultation room, Stores 		Rs. 3.5 m

Dispensary, Clinic room, Observation unit,

Utility room & toilets

Restoring of electricity, water supply and communication			Rs. 0.5 m

Medical Officers quarters 							Rs. 2.5 m

Equipment (  annexure ..)							Rs. 0.5 m

-----------

Total					Rs.7.0 m

=======

Central Dispensary – Ahungalla 	Not functioning

Partly damaged,

Furniture &    equipment washed away

Water and electricity services have to be provided

Facilities need  to be re-established

OPD	-	Patient waiting room, Consultation room, Stores 		Rs. 3.5 m

Dispensary, Clinic room, Observation unit,

Utility room & toilets

Restoring of electricity, water supply and communication			Rs. 0.5 m

Medical Officers quarters 							Rs. 2.5 m

Equipment 									Rs. 0.5 m

-----------

Total					Rs.7.0 m

=======

Gramodaya Health Centre – Dodanduwa		Not functioning

Partly damaged

Washed off- furniture &    equipment

Water and electricity services have to be provided

Facilities need  to be re-established:	(Please refer Annex 3)

Building –  	Clinic centre with waiting room, examination room

Store room, Injection room & toilets 				Rs. 3.5 m

Public Health Midwife’s quarters

Equipment							Rs. 0.5 m

Furniture							Rs. 0.2 m

Water & electricity						Rs. 0.3 m

-----------

Total 			Rs. 4.5 m

=======

Gramodaya Health Centre – Akurala	Not functioning

Partly damaged

Washed off- furniture &    equipment

Water and electricity services have to be provided

Facilities need  to be re-established:	(Please refer Annex 3)

Building –  	Clinic centre with waiting room, examination room

Store room, Injection room & toilets 				Rs. 3.5 m

Public Health Midwife’s quarters

Equipment							Rs. 0.5 m

Furniture							Rs. 0.2 m

Water & electricity						Rs. 0.3 m

-----------

Total 			Rs. 4.5 m

=======

Gramodaya Health Centre – Godagama		Not functioning

Partly damaged

Washed off- furniture &    equipment

Water and electricity services have to be provided

Facilities need  to be re-established:	(Please refer Annex 3)

Building –  	Clinic centre with waiting room, examination room

Store room, Injection room & toilets 				Rs. 3.5 m

Public Health Midwife’s quarters

Equipment							Rs. 0.5 m

Furniture							Rs. 0.2 m

Water & electricity						Rs. 0.3 m

-----------

Total 			Rs. 4.5 m

=======

Gramodaya Health Centre – Seenigama		Not functioning

Partly damaged

Washed off- furniture &    equipment

Water and electricity services have to be provided

Facilities need  to be re-established:	(Please refer Annex 3)

Building –  	Clinic centre with waiting room, examination room

Store room, Injection room & toilets 				Rs. 3.5 m

Public Health Midwife’s quarters

Equipment							Rs. 0.5 m

Furniture							Rs. 0.2 m

Water & electricity						Rs. 0.3 m

-----------

Total 			Rs. 4.5 m

=======

Gramodaya Health Centre – Hikkaduwa		Not functioning

Partly damaged

Washed off- furniture &    equipment

Water and electricity services have to be provided

Facilities need  to be re-established:	(Please refer Annex 3)

Building –  	Clinic centre with waiting room, examination room

Store room, Injection room & toilets 				Rs. 3.5 m

Public Health Midwife’s quarters

Equipment							Rs. 0.5 m

Furniture							Rs. 0.2 m

Water & electricity						Rs. 0.3 m

-----------

Total 			Rs. 4.5 m

=======

Gramodaya Health Centre – Madampagama

Not functioning

Partly damaged

Washed off- furniture &    equipment

Water and electricity services have to be provided

Facilities need  to be re-established:	(Please refer Annex 3)

Building –  	Clinic centre with waiting room, examination room

Store room, Injection room & toilets 				Rs. 3.5 m

Public Health Midwife’s quarters

Equipment							Rs. 0.5 m

Furniture							Rs. 0.2 m

Water & electricity						Rs. 0.3 m

-----------

Total 			Rs. 4.5 m

=======

Gramodaya Health Centre – Kalupe	Not functioning

Partly damaged

Washed off- furniture &    equipment

Water and electricity services have to be provided

Facilities need  to be re-established:	(Please refer Annex 3)

Building –  	Clinic centre with waiting room, examination room

Store room, Injection room & toilets 				Rs. 3.5 m

Public Health Midwife’s quarters

Equipment							Rs. 0.5 m

Furniture							Rs. 0.2 m

Water & electricity						Rs. 0.3 m

-----------

Total 			Rs. 4.5 m

=======

Gramodaya Health Centre – Pitiwela		Not functioning

Partly damaged

Washed off- furniture &    equipment

Water and electricity services have to be provided

Facilities need  to be re-established:	(Please refer Annex 3)

Building –  	Clinic centre with waiting room, examination room

Store room, Injection room & toilets 				Rs. 3.5 m

Public Health Midwife’s quarters

Equipment							Rs. 0.5 m

Furniture							Rs. 0.2 m

Water & electricity						Rs. 0.3 m

-----------

Total 			Rs. 4.5 m

=======

Gramodaya Health Centre – Kathaluwa		Not functioning

Partly damaged

Washed off- furniture &    equipment

Water and electricity services have to be provided

Facilities need  to be re-established:	(Please refer Annex 3)

Building –  	Clinic centre with waiting room, examination room

Store room, Injection room & toilets 				Rs. 3.5 m

Public Health Midwife’s quarters

Equipment							Rs. 0.5 m

Furniture							Rs. 0.2 m

Water & electricity						Rs. 0.3 m

-----------

Total 			Rs. 4.5 m

=======

Gramodaya Health Centre – Habaraduwa		Not functioning

Partly damaged

Washed off- furniture &    equipment

Water and electricity services have to be provided

Facilities need  to be re-established:	(Please refer Annex 3)

Building –  	Clinic centre with waiting room, examination room

Store room, Injection room & toilets 				Rs. 3.5 m

Public Health Midwife’s quarters

Equipment							Rs. 0.5 m

Furniture							Rs. 0.2 m

Water & electricity						Rs. 0.3 m

-----------

Total 			Rs. 4.5 m

=======

Gramodaya Health Centre – Ahangama 	Not functioning

Partly damaged

Washed off- furniture &    equipment

Water and electricity services have to be provided

Facilities need  to be re-established:	(Please refer Annex 3)

Building –  	Clinic centre with waiting room, examination room

Store room, Injection room & toilets 				Rs. 3.5 m

Public Health Midwife’s quarters

Equipment							Rs. 0.5 m

Furniture							Rs. 0.2 m

Water & electricity						Rs. 0.3 m

-----------

Total 			Rs. 4.5 m

=======

DPDHS Office	Building and vehicles completely went under water. The office has to relocate as the old building structures are not suitable to house the office.

Building							Rs. 50 million

Furniture & Equipment:-

Air conditioned conference room

Conference table with PA system

Computer system with 10 ten terminals

2 Photocopiers (1heavy duty)

1 Risograph

Office furniture

Fax machine

2 typewriters

Stationary

Filing cabinet

Steel cabinet

Iron safe

Standby generator						Rs 30 million

Refrigerators- 2

Television – 1

DVD player – 1

Video player – 1

Multimedia Projectors– 1

Magee boards – 5

Overhead projectors -2

Digital camera – 1

Water filters - 3

Electric Kettles – 3

Crockery

Cutlery

Intercom system(25 nodes)

Vehicles

Lorries – 2

DPD vehicle – 1

Regional Epidemiologist – 1

MO/MCH – 1

Regional Dental Surgeon -1					Rs 50.0 million

Health Education Officer – 1

Vans – 2

Van with audio visual equipment -1

Anti Rabies Campaign – 2

Total		Rs 130.0 million

Regional Training Centre – Southern Province

Building and vehicles went under water. The structure of the old building is not suitable to house the training centre. The training centre has to be relocated..

Building									Rs. 50 million

Lecture halls,

Office building

Training labs

Computer lab

Residential facilities for trainees

Furniture & Equipment:-

Air conditioned conference room

Conference table with PA system

Computer lab with 20 ten terminals

2 Photocopiers (1heavy duty), 1 Risograph

Office furniture, Fax machine	, 2 typewriters

Stationary, Filing cabinets, Steel cabinets

Iron safe, 									Rs 30 million

Refrigerators- 2, Television – 1, DVD player – 1

Video player – 1, Multimedia Projectors– 1

Magee boards – 5, Overhead projectors -2

Digital camera – 1, Water filters - 3

Electric Kettles – 3, Crockery, Cutlery

Intercom system(25 nodes)

Vehicles:

One passenger Van						Rs 4.0 m

Total			Rs 84.0 m

Cost estimates for re construction of Government Medical Institutes in

Galle District

| Institute | Cost Rs (million) |
| --- | --- |
| MOH Office - Hikkaduwa | 33.0 m |
| MOH Balapitiya | 33.0 m |
| RH - Madampegama | 8.5 m |
| Central Dispensary - Ahangama | 7.0 m |
| Occupational Health Centre Habaraduwa | 33.0 m |
| Central Dispensary - Ahungalla | 7.0 m |
| Central Dispensary - Hikkaduwa | 7.0 m |
| DPDHS Office Galle | 130.0 m |
| Port Health Office Galle Port | 33.0 m |
| Gramodaya Health Centre- Dodanduwa | 4.5 m |
| Gramodaya Health Centre- Akurala | 4.5 m |
| Gramodaya Health Centre- Godagama | 4.5 m |
| Gramodaya Health Centre- Seenigama | 4.5 m |
| Gramodaya Health Centre- Hikkaduwa | 4.5 m |
| Gramodaya Health Centre- Madampagama | 4.5 m |
| Gramodaya Health Centre- Kalupe | 4.5 m |
| Gramodaya Health Centre- Kathaluwa | 4.5 m |
| Gramodaya Health Centre- Habaraduwa | 4.5 m |
| Gramodaya Health Centre- Ahangama | 4.5 m |
| Gramodaya Health Centre- Pitiwela | 4.5 m |
| Regional Training Centre Galle | 84.0 m |
| Teaching Hospital Mahamodara | 1532.0 m |
| Total | 1957.0 m |

Kalutara District

The district of Kalutara belongs to the Western Province of Sri Lanka and among the three districts in the province has the largest extent of land. The district comprises of 14 Divisional Secretariat divisions, administratively covering 762 Grama Seva Niladhari divisions.

Kalutara has nine MOH divisions and of these Beruwala and Kalutara MOH areas are administered by The National Institute of Health Sciences (NIHS). The others come under the DPDHS of the area.

Two clinic centres in Aluthgama and Maradana that comes under the NIHS were totally damaged. Two Gramodya Health Centres in the district in Uyankele and Sagarapedesa were also damaged.

The Panadura base hospital which is the largest health institution in the area suffered indirect effects of the Tsunami tidal wave when the corridor of the mortuary was damaged during the high activity period.

Kalutara District Damages

National Institute of Health Sciences Division

Aluthgama Clinic Centre	Not functioning

Buildings are damaged completely

All the equipment washed off

Water and electricity services have to be provided

Buildings  -	Waiting hall

Examination Hall		Rs. 5.0 m

Store room

Injection room

PHI’s office

PHNS’s Office

PHM’s Residence

Equipment	Furniture

Electricity			Rs. 2.0 m

Water system

-----------

Total				Rs. 7.0 m

=======

Maradana Clinic Centre	Not functioning	 Need re-location

Completely damaged

All the equipment washed off

Water and electricity services have to be provided

Buildings  -	Waiting hall

Examination Hall		Rs. 5.0 m

Store room

Injection room

PHI’s office

PHNS’s Office

PHM’s Residence

Equipment	Furniture

Electricity			Rs. 2.0 m

Water system

-----------

Total				Rs. 7.0 m

=======

Gramodaya Health Centre – Uyankelle	Not functioning

Partly damaged

Furniture & equipment washed off.

Water and electricity services have to be provided

Facilities need to be re-established		(Please refer Annex 3)

Building –  	Clinic centre with waiting room, examination room

Store room, Injection room & toilets 				Rs. 3.5 m

Public Health Midwife’s quarters

Equipment							Rs. 0.5 m

Furniture							Rs. 0.2 m

Water & electricity						Rs. 0.3 m

-----------

Total 			Rs. 4.5 m

=======

Deputy Provincial Director of Health Services Kalutara Division:

Gramodaya Health Centre – Sagaea Pedesa	Not functioning

Partly damaged , Furniture & equipment washed off.

Water and electricity services have to be provided

Facilities need  to be re-established		(Please refer Annex 3)

Building –  	Clinic centre with waiting room, examination room

Store room, Injection room & toilets 				Rs. 3.5 m

Public Health Midwife’s quarters

Equipment							Rs. 0.5 m

Furniture							Rs. 0.2 m

Water & electricity						Rs. 0.3 m

-----------

Total 			Rs. 4.5 m

=======

Gramodaya Health Centre – Magalkanda		Not functioning

Partly damaged , Furniture & equipment washed away

Water and electricity services have to be provided

Facilities need  to be re-established:	(Please refer Annex 3)

Building –  	Clinic centre with waiting room, examination room

Store room, Injection room & toilets 				Rs. 3.5 m

Public Health Midwife’s quarters

Equipment							Rs. 0.5 m

Furniture							Rs. 0.2 m

Water & electricity						Rs. 0.3 m

-----------

Total 			Rs. 4.5 m

=======

Panadura Base Hospital

*Indirect effects ( Corridor of the Mortuary building damaged)		Rs. 1.0 m

=======

Cost estimates for re construction of Government Medical Institutes in

Kalutara District

| Institute | Cost Rs (million) |
| --- | --- |
| Aluthgama Clinic Centre | 7.0 m |
| Maradana Clinic Centre | 7.0 m |
| Uyankelle Gramodaya Health Centre | 4.5 m |
| Sagara Pedesa Gramodaya Health Centre | 4.5 m |
| Magalkanda Gramodaya Health Centre | 4.5 m |
| Panadura Base Hospital | 1.0 m |
| Total | 28.5 m |

Colombo District

The Tsunami tidal wave that devastated Sri Lanka did not spare even the country’s capital city and district Colombo.

Three Gramodya Health centres in Modera, Egoda Uyana and Katukurunda which were situated close to the beach were totally destroyed. Even though they are only Gramodya Health Centres they serve a large population as they are situated in highly populated areas.

Colombo District Damages

Moratuwa MOH Area

Gramodaya Health Centr - Modera 	Not functioning

Partly damaged

Furniture & equipment washed away

Facilities need  to be re-established:

Building –  	Clinic centre with waiting room, examination room

Store room, Injection room & toilets 				Rs. 3.5 m

Public Health Midwife’s quarters

Equipment							Rs. 0.5 m

Furniture							Rs. 0.2 m

Water & electricity						Rs. 0.3 m

-----------

Total 			Rs. 4.5 m

=======

Gramodaya Health Centre - Egoda Uyana 	Not functioning

Partly damaged

Furniture & equipment washed away

Facilities need  to be re-established:	(Please refer Annex 3)

Building –  	Clinic centre with waiting room, examination room

Store room, Injection room & toilets 				Rs. 3.5 m

Public Health Midwife’s quarters

Equipment							Rs. 0.5 m

Furniture							Rs. 0.2 m

Water & electricity						Rs. 0.3 m

-----------

Total 			Rs. 4.5 m

=======

Gramodaya Health Centr - Katukurunda 	Not functioning

Partly damaged

Furniture & equipment washed away

Facilities need  to be re-established:	(Please refer Annex 3)

Building –  	Clinic centre with waiting room, examination room

Store room, Injection room & toilets 				Rs. 3.5 m

Public Health Midwife’s quarters

Equipment							Rs. 0.5 m

Furniture							Rs. 0.2 m

Water & electricity						Rs. 0.3 m

-----------

Total 			Rs. 4.5 m

=======

Gramodaya Health Centre - Angulana 	Not functioning

Partly damaged

Furniture & equipment washed away

Facilities need  to be re-established:	(Please refer Annex 3)

Building –  	Clinic centre with waiting room, examination room

Store room, Injection room & toilets 				Rs. 3.5 m

Public Health Midwife’s quarters

Equipment							Rs. 0.5 m

Furniture							Rs. 0.2 m

Water & electricity						Rs. 0.3 m

-----------

Total 			Rs. 4.5 m

=======

Gramodaya Health Centre - Uyana 	Not functioning

Partly damaged

Furniture & equipment washed away

Facilities need  to be re-established:	(Please refer Annex 3)

Building –  	Clinic centre with waiting room, examination room

Store room, Injection room & toilets 				Rs. 3.5 m

Public Health Midwife’s quarters

Equipment							Rs. 0.5 m

Furniture							Rs. 0.2 m

Water & electricity						Rs. 0.3 m

-----------

Total 			Rs. 4.5 m

=======

Cost estimates for re construction of Government Medical Institutes in

Colombo District

| Institute | Cost Rs (million) |
| --- | --- |
| Gramodaya Health Centre Modera | 4.5 m |
| Gramodaya Health Centre Egoda Uyana | 4.5 m |
| Gramodaya Health Centre Katukurunda | 4.5 m |
| Gramodaya Health Centre Angulana | 4.5 m |
| Gramodaya Health Centre Uyana | 4.5 m |
| Total | 22.5 m |

Damage to drugs and medical supplies due to the tsunami disaster

Government spends a substantial proportion of its health care budget on drugs and supplies. The recent Tsunami disaster caused enormous damage to the health care infrastructure and along with that damaged significant proportion of drugs and supplies in those facilities. Two regional drug stores belonging to the government were completely destroyed. The supplies include pharmaceuticals, surgical dressings, X-ray items, surgical and dental disposables, and laboratory consumables. Damage was also caused to non-consumable items include surgical, dental and laboratory instruments. The total loss of consumables and non-consumables can be estimated as Rs. 172,939,407/- or US $ 1.73 million. Damage to the consumables and non-consumables in the affected government health care institutions need to be rectified.

| Value of lost medical items in Tsunami affected areas (MSD Supplies) |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- |
|  | Division / Institution |  | Value of Consumable (Rs) |  | Value of Non –Consumables (Rs) |
| 1 | Galle DPDHS |  | 9,870,354.00 |  | 374,733.00 |
| 2 | Mahamodara Teaching Hospital |  | 39,641,878.00 |  | 581,877.00 |
| 3 | Matara DPDHS |  | 30,174,454.00 |  | 958,146.00 |
| 4 | Hambantota DPDHS |  | 15,549,301.00 |  | 1,134,109.00 |
| 5 | Kalmunai DPDHS |  | 27,049,832.00 |  | 147,584.00 |
| 6 | Batticaloa DPDHS |  | 9,693,621.00 |  | 103,967.00 |
| 7 | Trincomalee DPDHS |  | 10,755,683.00 |  | 940,659.00 |
| 8 | Mullaitivu DPDHS |  | 19,676,830.00 |  | 156,116.00 |
| 9 | Jaffna DPDHS |  | 6,048,467.00 |  | 91,806.00 |
|  | Total |  | 168,450,420.00 |  | 4,488,987.00 |
| Calculated loss of consumables (Note 1) |  |  |  | 168,450,420.00 |  |
| Calculated loss of non-consumables (Note 2) |  |  |  | 4,488,987.00 |  |
| Total Calculated loss |  |  |  | 172,939,407.00 |  |
| Note 1 |  | Consumables include pharmaceuticals, surgical dressings, X-Ray items, surgical disposables, dental disposables and laboratory consumables |  |  |  |
| Note 2 |  | Non consumables include surgical instruments, dental instruments and laboratory instruments |  |  |  |
| Basis |  | 2,3,5,&8 – 100% consumables + 100% of non consumables |  |  |  |
|  |  | 1,4,6,7,&9 - 25% consumables + 50% of non consumables |  |  |  |

Annexure 1

Building requirement for a District Hospital

Out Patient Department with patient waiting halls

(Consultation rooms, Injection room, dressing room etc)

Pharmacy

Clinic room

Administration block for the office

Emergency Treatment Unit

Dental Unit								6000 sq ft

Health Education Unit

Hospital Record room

Hospital Library

Doctors duty room

Laboratory

Mini Operation Theater

Male ward -30 beds

Female ward – 30 beds

Peadiatric Ward – 20 beds

Maternity Ward – 20 antenatal beds, 10 post natal beds		24000 sq ft

Labour Room – two beds

Kitchen

Drug store

General Store

Ambulance garage with driver’s quarters				2000 sq ft

Mortuary

Generator house with a stand by generator

Connecting corridors

District Medical Officer’s quarters					2500 sq ft

Twin Quarters for Medical Officers					4600 sq ft

PHM’s quarters							1300 sf ft

Nurses quarters (10 rooms for 2 nurses each) 			3200 sq ft

Technical staff’s quarters						3200 sq ft

Minor employee quarters						3200 sq ft

Total space	50,000 sq ft

Construction cost @ Rs 3000/= per sq ft		Total cost 	Rs 150,000,000.00

Water tank with a sump or a large well

Water pump house with pumping motors				Rs 10,000,000.00

Sewerage system

Waste management system with an incinerator 			Rs 2,000,000.00

Annexure 2

Equipment requirement for a District Hospital

| Equipment | Number |
| --- | --- |
| Ambubag and Masks | 5 |
| Auroscope | 3 |
| Autoclave (Mini) | 1 |
| Autoclave (Dental) | 1 |
| Basic intant Inclubators | 1 |
| Beds Side Monitor/ Defibrillators | 1 |
| Centrifuge | 1 |
| Clinical examination torch | 4 |
| Clinical thermometers (oral) | 4 |
| CTG | 1 |
| Cupboard for Consumables | 1 |
| Cutdown set | 2 |
| Cut-down set Tracheaostomy set | 5 |
| Delivery Kids | 1 |
| Dental Unit & Chair | 1 |
| Dressing set | 6 |
| Dressing Trolley | 3 |
| Drying Cupboard | 1 |
| Doppler Detector | 1 |
| ECG Recorders | 1 |
| ECG monitor 1 Pulse oxymeter | 1 |
| ECG Beds Side Monitor | 1 |
| Electronic Laboratory Balance | 1 |
| Endo Tracheal Tubes | 1 |
| Examination lamp | 4 |
| Foetal Doppler Detector | 1 |
| Foetal Stethoscope | 3 |
| Forceps: Catch, Artery, Chetles, Rat-tooth | 5 each |
| Pulse Oxymeter | 1 |
| Glocometer | 1 |
| Height measuring tape | 4 |
| Hot Air Oven | 1 |
| Hot Plate | 1 |
| Incubators (Basic - Infant) | 1 |
| Infant warmer | 1 |
| Infusion Pump | 1 |
| Infusion pump 1 Sterilizer | 1 |
| Infusion pump 1 Sucker | 1 |
| Jars | 5 |
| Knee hammer | 4 |
| Light Curing Machine | 1 |
| Labour room delivery kits | 1 |
| Laryngoscope | 1 |
| Mayo,s Trolley | 1 |
| Medicine Trolley | 5 |
| Mattresses | 125 |
| Micro-motor (Air turbine/ air rotor) | 1 |
| Microscop | 1 |
| Mini Auot Clever | 1 |
| Nebulizers | 2 |
| Ophthalmoscope | 3 |
| P. Sphygmomanometers | 1 |
| PP cutter | 1 |
| Proctoscope | 2 |
| Pulse Oxymeter | 1 |
| Refrigerator | 1 |
| Spectrophotometer | 1 |
| Speculum | 2 |
| Sphygmomanometer | 9 |
| Spot lamp (Ward) | 3 |
| Spot lamp( OT) | 2 |
| Sterilizer (Large) | 2 |
| Sucker 1 Laryngoscope | 1 |
| Suction apparatus | 1 |
| Suction apparatus (portable) | 1 |
| Table top autoclave | 1 |
| Tongue depressors (metal) | 8 |
| Torch | 4 |
| Trays: Kidney, Rectangular, other | 5 |
| Ultrasonic Scaler | 1 |
| Vacuum extractor(Manual & electrical) | 1 |
| Vaginal speculums and Other surgical instruments | 5 |
| Water Distiller | 1 |
| Weighing scale (Infant2, Adult6, child2.) | 10 |
| X ray illuminator | 1 |
| X ray machine (330ma - Mobile or Static) | 1 |

Annexure 3

Building requirement for a Gramodaya Health Centre (GHC)

Clinic room with patient waiting halls

Examination room

General Store								 1750 sq ft

PHM’s quarters

Total space	1750 sq ft

Construction cost @ Rs 2000/= per sq ft		Total cost 	Rs 3,500,000.00

Equipment necessary for  Gramodaya Health Centre

- Chairs – for staff 5

for clients( with back rest) 30

- Tables 3

- Cupboards with locks 2

- Filing cabinet 01

- Examination bed 01

- FP / IUCD bed 01

- Small benches 2

- Dustbins 2

- Sharps disposal bin

- Pail

- Filter

- Book rack

- Display board

- Notice board

- Miscellan.     Brooms 02

Rugs 03

Toilet brush 01

Floor brush 01

Brush to wipe away water 01

Vim/ Harpic

Soap

Plastic bucket

Bowl

Curtains

Linen		Bed Sheets 4

Towels 8

Mackintosh  2

Table cloth 5

GS  Towels 12

Adult weighing scales 1

Sica weighing scales    1

Spring balance (salter) 1

Height measuring scale 1

Length measuring board 1

BP Apparatus 1

Stethoscope 1

Pinnard       1

Tape   1

Steam steriliser

AD syringes

Urine test kits

Syringes

0-0.05 cc    10

0-5 cc          80

2cc syringes with 22 gauge needles  - Number based on clients for Depoprovera

Needles

23/ 24 G, 26 G, 18 G

Hot plate (If no electricity – Kerosene lamp and plastic bottle to store kerosene)

If no water- Buckets  2,    Bowls  2,  Basins  2

Catch forceps 2

Jars 2

Stainless steel bowls  5  ( to store different vaccines)

Vaccine Carriers

Play material

Indoor- with low cost material

Outdoor-  Swings

See- saw

Rotating play equipment  1

Climbing frame – 3 feet in height

Sliding mat – 4 feet in height

IEC material

Magi board   with health message

Reading material

Health education material made locally

Flash cards

Calender type material

FP items

Demonstrations

Annexure 4

Building requirement for a Office of the Medical Officer of Health (MOH)

Clinic rooms

Injection room

Examination room with toilet facilities

IUD clinic room

Waiting hall with toilet facilities

General stores

General office								6000 sq ft

Office space for the MOH

Office space for the Assistant MOH

Office space for the Public Health Nursing Sister

Office space for the Supervising Public Health Midwife

Office space for the Supervising Public Health Inspector

Conference room

Garage

Security Guard Room

Boundary walls

Quarters of the MOH							2500 sq ft

Quarters for the PHNS						1500 sq ft

Total 		10,000 sq ft

Annexure 5

PROPOSED VIHARAMAHADEVI MATERNITY & WOMEN HOSPITAL AT KARAPITIYA

(Estimate prepared by Central Engineering Cousultancy Bureau, Colombo Sri Lanka)

| Ser. No. | Description | Area Sq Meters | Cost (million) Sri Lankan Rupees) | Cost (million) (US $) |
| --- | --- | --- | --- | --- |
| 01 02 03 04 05 06 07 08 09 10 11 12 13 14 15 16 17 18 19 20 | ## Package 1 Maternity & Gynaecology Unit (750 bed) including IVF + Mini theatre + Cancer Unit # Sub Total – 1 ## Package 2 NICU + SICU + PBU Blood Bank Path Lab + Scanning Unit X Ray Unit Oxygen Room # Sub Total – II ### Package 3 Clinic Facilities General Stores Administration + Library + Auditorium Ambulance Garage + Drivers rest room + Kitchen + Workshop # Sub Total – III ## Package 4 Laundry + CSD Water Sump + Generator Services : 1.Waste water treatment 2.Sewerage treatment 3.Incinerator for Bio Medical waste & General garbage Mortuary Parking + Access Road + Boundary Wall # Sub Total – IV ## Package 5 Cleaning + Security Block Changing Block for Hospital Staff Quarters Utility Building, Bank, Post Office, Canteen & Police Post # Sub Total – V Total Amount (Sub Total I +II +III +IV +V) | 10000 2000 300 500 100 1500 600 2000 | 375 ---------------- 375 ========== 70 10 15 5 10 ----------------- 110 ========== 40 15 40 15 15 ----------------- 125 ========== 15 20 20 8 20 ---------------- 83 ============ 5 10 150 10 --------------------- 175 ============ --------------------- 868 ============ | ---------------3.57 ========= --------------- 10.5 ========= -------------- 1.19 ======== -------------- 0.79 ========== ------------------ 1.67 ========== ------------------ 8.27 ========== |

Note : 1. This estimate does not include any Taxes, Consultancy Fee & hospital equipment cost

2. 105 Sri Lankan Rupees = 01 US Dollars

Annexure 5a

Equipment for Proposed Women’s Hospital – Karapitya, Galle, Sri Lanka

#### Approximate Estimate

1.	Hospital beds, lockers, patient drug & linen trolleys etc.	=	60 Million SL Rupees

2.	Labour Room equipment				=	70 Million SL Rupees

3.	Operation Theatre equipment				=	75 Million SL Rupees

4.	Operation Theatre Instruments				=	35 Million SL Rupees

5.	Surgical Intensive Care Unit				=	60 Million SL Rupees

6.	Premature Baby Unit					=	25 Million SL Rupees

7.	Neonatal Intensive Care Unit				=	45 Million SL Rupees

8.	In Vitro Fertilization Lab				=	30 Million SL Rupees

9.	Pathology Lab						=	15 Million SL Rupees

10.	Blood Bank						=	5 Million SL Rupees

11.	Air –conditioning of relevant areas			=	10 Million SL Rupees

(operation theatre, IVF lab etc.)					----------------------------

=	430 Million SL Rupees

Add 10% as the above estimates are based on rates more than two (2) years ago

Therefore total estimate approximately			=	475 Million SL Rupees

(US$ 4.5 Million)

=================

Annexure 6

PROPOSED WARD COMPLEX FOR GENERAL HOSPITAL AT TRINCOMALEE

8 wards  (576 beds)

NICU + SICU + PBU

Blood Bank

Path Lab + Scanning Unit

X Ray Unit

Oxygen Room

Laundry + CSD

Water Sump + Generator					100,000 sq ft

Services :

1.Waste water treatment

2.Sewerage treatment

3.Incinerator for Bio Medical waste &

General garbage

Parking + Boundary Wall

Total space	100,000 sq ft

Construction cost @ Rs 3000/= per sq ft		Total cost 	Rs 300,000,000.00

Sewerage system for the hospital			Rs 200,000,000.00

Equipment for Proposed Ward complex at GH Trincomalee

#### Approximate Estimate

1.	Hospital beds, lockers, patient drug & linen trolleys etc.	=	50 Million SL Rupees

2.	Labour Room equipment				=	25 Million SL Rupees

3.	Operation Theatre equipment				=	75 Million SL Rupees

4.	Operation Theatre Instruments				=	25 Million SL Rupees

5.	Surgical Intensive Care Unit				=	25 Million SL Rupees

6.	Premature Baby Unit					=	25 Million SL Rupees

7.	Neonatal Intensive Care Unit				=	25 Million SL Rupees

Total		=	250 Million SL Rupees

Vehicles for  GH Trincomalee

Ambulances 2

Lorry 1								Rs 10.0 mn

This proposal contains estimated cost of the repairs to the damaged Government Health Institutions only.

Apart from the cost estimates given in this proposal the cost of restoration of central supplies, epidemiological surveillance, laboratory services, maternal, child health, family planning, immunization services and other preventive health services have to be assessed. Also hospitals in adjacent areas have to strengthen in order to take over the additional workload of the displaced population until the services are restored in affected areas.

# A comprehensive detail proposal for this effect is being prepared and will be published in due course.

# Abbriviatons

AMO		 Assistant Medical Officer

BH		 Base Hospital

CD & MH 	Central Dispensary & Maternity Home

CD		Central Dispensary

DH		District Hospital,

DPDHS	Deputy Provincial Director Health Services

DMO		District Medical Officer,

GH 		General Hospital,

GHC		Gramodaya Health Centre

HEU 		 Health Education Unit

HEO		 Health Education Officer

MO –		 Medical Officer

MOH		 Medical Officer of Health

MCH Clinic	Maternal and Child Health Clinic

MO/MCH	Medical Officer/ Maternal and Child Health

NO		Nursing Officer

NIHS		National Institute of Health Sciences

OPD		Out Patient Department,

OHC		Occupational Health Centre

PDHS		Provincial Director Health Services

PU		Peripheral Unit,

PHI		Public Health Inspector

PHM		Public Health Midwife

PHN		Public Health Nurse

PHNS		Public Health Nursing Sister

PHO		Port Health Office

RE		Regional Epidemiologist

RDS		Regional Dental Surgeon

RH		Rural Hospital

RMSD		Regional Medical Supplies Division

RCS		Regional Training Centre

SPHM		Supervising Public Health Midwife

TH		Teaching Hospital